## Instructions
GC APPLICATION FOR PAYMENT — Instructions
WHAT THIS WORKBOOK IS
Monthly billing workbook for a General Contractor billing the Owner against the prime contract. Mirrors AIA G-702 (Application + Certificate for Payment, the one-page summary the Owner / Architect signs) and G-703 (Continuation Sheet, the line-item detail). Use as the GC-side parallel of the sub's Sub_Schedule_of_Values.xlsx in the Universal Sub Suite.
ONE-TIME SETUP AT AWARD
1. Project Info: project name, owner, architect, contract date, Original Contract Sum, retainage rate, billing cycle.
2. SOV Setup: line items. Usually mirror the Trade Bids tab from GC_Bid_Estimator.xlsx (copy/paste line items + scheduled values). Sum of scheduled values must equal Current Contract Sum on Project Info (the workbook validates this).
MONTHLY WORKFLOW
1. Open G-703 Pay App — Current at the end of each billing period.
2. Enter % Complete This Period for each line item (column F). Workbook computes this-period $, total-to-date $, retainage, and net amount due.
3. Update Stored Materials Log for any billed-but-not-installed materials.
4. Open G-702 Summary — Current. Verify the auto-populated totals.
5. Print BOTH tabs (G-703 + G-702) for transmittal to Architect + Owner.
6. After Owner pays, copy column G (Total To Date) values into the next month's column on Pay App History.
RETAINAGE
Default retainage rate is set on Project Info (10% commercial standard; 5% on many state public works). The workbook supports either of two retention treatments — set 'Retain on stored materials?' on Project Info to Yes or No. If the contract allows retention reduction at 50% completion, keep the rate at 10% here and reduce it on the specific pay app where reduction is requested.
RELATIONSHIP TO GC BID ESTIMATOR
The SOV here is the line-item dollar values you ultimately accepted from the Bid Estimator's Trade Bids + Self-Perform + General Conditions roll-up. To set up:
- Open GC_Bid_Estimator.xlsx
- Trade Bids tab: pull each Line Total ($) into a row on SOV Setup here
- Self-Perform tab: pull each Line Total ($) into a row on SOV Setup
- General Conditions: usually combined into 1-3 SOV lines (Supervision, Field Office, etc.)
- Add OH + Profit + Bond + Sales Tax as separate SOV lines if Owner requires line-item detail
CHANGE ORDERS
Approved change orders are added as ADDITIONAL SOV lines (prefixed 'CO #'). Do NOT modify the Original Contract Sum line items. The Current Contract Sum field on Project Info captures the running total (Original + COs).
TROUBLESHOOTING
- SOV Setup totals don't equal Contract Sum: cross-check each line, confirm no rows are blank or missing values. The validation banner at the bottom of Project Info will flag this.
- Retainage on Pay App doesn't match Architect's calc: confirm retainage rate matches the prime contract, and confirm 'Retain on stored materials?' setting matches.
- 'Variance' column on SOV Setup shows red (over-billed): you billed more than scheduled for a line. Reduce billing OR add a change order on SOV Setup for the overage.

## Project Info
PROJECT INFORMATION — GC PAY APP
Project Name
Project No. (GC's)
Owner
Owner Address
Architect
General Contractor (this firm)
GC Address
Prime Contract No.
Prime Contract Date
Original Contract Sum | 0
Approved Change Orders to Date | 0
Current Contract Sum (Orig + COs)
Retainage Rate (%) | 10%
Retain on Stored Materials? | No
Pay App Submission Day of Month | 25
Owner Payment Terms (days after Architect cert) | 30
Project Manager (GC)
Architect Project Manager
SOV TOTAL VALIDATION
SOV Setup line-item total:
Current Contract Sum:
Variance (should be $0):

## SOV Setup
SOV SETUP — Schedule of Values Line Items
One row per Contract line item. Scheduled Value must sum to Current Contract Sum on Project Info. Typically copy from GC_Bid_Estimator.xlsx Trade Bids + Self-Perform + General Conditions. Add change orders as separate rows prefixed 'CO #'.
Line # | Description | CSI Div | CSI Section | Scheduled Value ($) | % of Contract | Billed To Date ($) | Balance to Finish ($) | Variance | Type | Notes
TOTAL

## G-703 Pay App
G-703 — Continuation Sheet (Pay App Detail)
Project: =ProjectName | [5 empty] | Pay App #: | 1 | Period Ending:
Line # | Description | CSI Div | Scheduled Value | Previous Periods ($) | % Complete This Period | This Period ($) | Total Completed To Date ($) | Materials Stored ($) | Total + Stored ($) | % Complete | Retainage ($) | Balance to Finish ($) | This Period Net Due ($)
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
|  |  |  | 0 | 0% |  |  | 0
GRAND TOTAL

## G-702 Summary
G-702 — APPLICATION & CERTIFICATE FOR PAYMENT
One-page Owner-facing summary. Prints with G-703 Pay App as the cover sheet. Architect signs the bottom to certify the amount due.
PROJECT
Project Name
To Owner
From Contractor
Contract No.
Pay App No.
Period Ending
CONTRACT SUMMARY
1. Original Contract Sum
2. Net Change by Change Orders
3. Contract Sum to Date (1+2)
4. Total Completed & Stored to Date
5. Retainage
6. Total Earned Less Retainage (4-5)
7. Less Previous Certificates for Payment
8. CURRENT PAYMENT DUE (6-7)
9. Balance to Finish, Plus Retainage
CONTRACTOR CERTIFICATION
The undersigned Contractor certifies that to the best of the Contractor's knowledge, information, and belief, the Work covered by this Application has been completed in accordance with the Contract Documents, that all amounts have been paid by the Contractor for Work for which previous Certificates for Payment were issued and payments received from the Owner, and that current payment shown herein is now due.
Contractor:
By: ____________________________ Title: ____________________ Date: __________
ARCHITECT'S CERTIFICATE
In accordance with the Contract Documents, based on on-site observations and the data comprising this application, the Architect certifies to the Owner that the Work has progressed as indicated, the quality of the Work is in accordance with the Contract Documents, and the Contractor is entitled to payment of the AMOUNT CERTIFIED.
AMOUNT CERTIFIED: $ ____________________________
Architect:
By: ____________________________ Date: __________

## Pay App History
PAY APP HISTORY — 12-Month Roll-Up
After each pay app is paid, transfer the Total + Stored values from the G-703 tab into the next column below.
Line # | Description | Scheduled Value | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12 | Final To Date
TOTAL

## Stored Materials
STORED MATERIALS LOG
Materials billed but not yet installed. Architect typically requires evidence of storage, insurance, segregation, and supplier lien waiver before approving stored materials in the pay app.
Date Added | SOV Line Ref | Description | Supplier | PO # | Quantity | Unit | Unit Cost | Total Value ($) | Storage Location | Insured? | Supplier Lien Waiver? | Date Installed | Status
TOTAL

## CSI Reference (hidden)
CSI MasterFormat Divisions
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities