## Instructions
GC PROJECT OPERATIONS — Instructions
WHAT THIS WORKBOOK IS
Single consolidated workbook covering the GC's day-to-day project execution: RFI Log, Submittal Log, Schedule/Lookahead, Daily Field Report Log, Punch List, and Meeting Minutes. Project Info is entered ONCE on the Project Info tab and pulled into every other tab via named ranges — you do not re-type project name, owner, GC, etc., across six different workbooks.
WHY CONSOLIDATED
These are all tools the SAME user (the GC's Project Manager) uses in the SAME workflow (project execution between award and closeout). Keeping them in one workbook means: shared header data, shared CSI dropdowns, single file to back up, single file to email to a covering super.
WHAT'S NOT IN HERE
- Bidding: use GC_Bid_Estimator.xlsx (different phase, different user — the estimator).
- Monthly billing to Owner: use GC_Application_for_Payment.xlsx (different cadence, different audience — Owner + Architect).
- Sub management: use Subcontractor_Tracker.xlsx (Business tier) for vendor master + COIs.
- Job cost accounting: use Job_Costing_Spreadsheet.xlsx (Business tier).
- Change Orders to subs: use Change_Order_Log.xlsx (Business tier).
WORKFLOW
1. Project Info: fill in once at award. Drives every other tab.
2. RFI Log: log RFIs sent to architect/engineer/owner. Track response cadence.
3. Submittal Log: track shop drawings, product data, samples, mockups through the approval cycle.
4. Schedule / Lookahead: high-level activity tracking with 3-week lookahead. Not a CPM tool — use P6/MS Project/Smartsheet for true CPM scheduling.
5. Daily Field Report Log: one ROW per day (not one tab per day). Crew counts, weather, key activities, issues. Use Daily_Field_Report.xlsx from Universal Sub Suite for per-day detail.
6. Punch List: track punch-list items from substantial completion to final acceptance.
7. Meeting Minutes: running log of all project meetings (Owner-Arch-GC, coordination, safety, subcontractor).
DESIGN NOTE
This workbook was deliberately consolidated AGAINST the 'one tool per file' pattern. The other ContrPro workbooks (Bid Estimator, Application for Payment, Sub SOV, T&M Tracker, etc.) are each their own files because they serve different users/phases. The operational tools all serve the GC PM during execution; consolidating them avoids the 'fill in project info six times' tax.

## Project Info
PROJECT INFORMATION — Shared Across All Tabs
Enter once. Every other tab references this data via named ranges.
Project Name
Project Address
Project No. (GC's)
Owner
Architect
Structural Engineer
MEP Engineer
Civil Engineer
General Contractor
Prime Contract No.
Prime Contract Date
Notice to Proceed Date
Anticipated Substantial Completion
Anticipated Final Completion
KEY PERSONNEL
Project Executive (GC)
Project Manager (GC)
Site Superintendent (GC)
Safety Officer (GC)
Owner's Rep
Architect Project Manager
RFI / SUBMITTAL SLA
RFI Response SLA (days, per contract) | 10
Submittal Review SLA (days, per contract) | 14
Resubmittal SLA (days, per contract) | 10

## RFI Log
RFI LOG
Project: =ProjectName GC: =GCName Architect: =ArchitectName RFI SLA: =RFI_SLA days
RFI # | Date Sent | From | To | CSI Div | Subject | Description | Response Due (auto) | Response Date | Days Open | Status | Cost Impact ($) | Sched Impact (days) | Resolution | Notes
SUMMARY
Total RFIs logged
Open
Resolved + Closed
Past SLA (open + days > SLA)
Total cost impact ($)
Total schedule impact (days)

## Submittal Log
SUBMITTAL LOG
Project: =ProjectName GC: =GCName Architect: =ArchitectName Submittal SLA: =SubmittalSLA days
Submittal # | Spec Section | Description | Type | Required by Date | Date Sent to Architect | Date Returned | Status | Resubmittal # | Final Approved Date | Days Out | Sub / Vendor | Notes

## Schedule
SCHEDULE / 3-WEEK LOOKAHEAD
Project: =ProjectName GC: =GCName Tracks high-level activities + milestones. NOT a CPM scheduling tool — use P6, MS Project, or Smartsheet for true CPM logic. This is for status reporting and weekly lookahead.
Activity ID | Activity / Milestone | Trade | CSI Div | Baseline Start | Baseline Finish | Actual / Forecast Start | Actual / Forecast Finish | Duration (days) | % Complete | Status | Predecessor IDs | Variance (days) | Notes

## DFR Log
DAILY FIELD REPORT LOG
Project: =ProjectName GC: =GCName Super: =GCSuper One ROW per day. For per-day detail (crew names, hours per worker, materials), use the Daily_Field_Report.xlsx from Universal Sub Suite (33-tab monthly workbook).
Date | Day | Weather AM | Weather PM | Temp °F (high/low) | Crew Count (Total) | Crews on Site (list) | Key Activities Today | Issues / Delays | Visitors | Safety Incidents | Inspections | Lost Hours (weather/delay) | Foreman / Super | Notes
DFR SUMMARY
Days logged
Total crew-days
Days with issues
Days with safety inc.
Total lost hours

## Punch List
PUNCH LIST
Project: =ProjectName GC: =GCName
Item # | Date Added | Source | Location | Trade | CSI Div | Description | Severity | Assigned To | Photo Ref | Date Completed | Verified By | Status | Notes
PUNCH LIST SUMMARY
Total items
Open
Awaiting Verification
Closed
Life-Safety items

## Meeting Minutes
MEETING MINUTES LOG
Project: =ProjectName GC: =GCName
Meeting # | Date | Type | Attendees | Topics Discussed | Decisions | Action Items | Action Owners | Next Meeting | Notes

## CSI Reference (hidden)
CSI MasterFormat Divisions
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities