Commercial GC scheduling operates on two distinct time horizons that work together: (1) the Baseline Schedule — the master Critical Path Method (CPM) schedule developed at project start, showing every activity from notice to proceed through final completion, with durations, dependencies, milestones, and float; and (2) the 3-Week Look-Ahead — a rolling short-interval schedule used at weekly trade coordination meetings to confirm what's happening in the next 21 days at the trade-by-trade level. The Baseline answers "are we on schedule overall?" The Look-Ahead answers "what's actually happening this week and who's responsible?" Both are required; they serve different audiences and different decisions. This package provides templates and discipline rules for both.

Two Time Horizons — Baseline vs. Look-Ahead

Baseline Schedule — Master CPM

3-Week Look-Ahead Schedule

Monthly Schedule Update Procedure

Schedule Discipline — 12 Rules

| Aspect | Baseline Schedule (CPM) | 3-Week Look-Ahead |
| --- | --- | --- |
| Time horizon | Notice to Proceed → Final Completion (typically 6–36 months) | Current week + next 2 weeks (21 calendar days) |
| Granularity | Activities of 1–14 days each, organized by phase / area / trade | Daily granularity at the trade-level work crew |
| Updated | Monthly (with each Application for Payment) | Weekly (every coordination meeting) |
| Audience | Owner, architect, lender (if any), GC project executive, surety | Trade subcontractor PMs and superintendents at the weekly coordination meeting |
| Decision it drives | "Are we on schedule overall? When is substantial completion? What's on the critical path?" | "What's happening this week and next? Who has what crew where? What conflicts need to be resolved?" |
| Software | Primavera P6, Microsoft Project, Asta Powerproject, Synchro | Excel, Smartsheet, P6 + filter, Asana / Monday for simple projects |
| Format | Gantt chart with logic ties; CSV export with predecessors / successors / float | Tabular by trade and by week; sometimes printed as 11x17 banner posted at job trailer |

The Baseline is developed in the first 30 days of the project. It identifies every activity required to complete the work, with durations, dependencies (predecessor → successor relationships), and milestone dates. The Critical Path is the longest sequence of dependent activities — any delay on the critical path delays the project; activities not on the critical path have float (the time they can slip without affecting the project end date).

| Act ID | Activity Description | Phase / Area | Trade | Duration (days) | Predecessor (relation) | Early Start | Early Finish | Float (days) | Critical? |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| — SAMPLE EXTRACT (typical 12-month commercial project; full schedule has 200–500 activities) — |  |  |  |  |  |  |  |  |  |
| A100 | Notice to Proceed | Pre-Con | — | 0 | — | 2026-03-01 | 2026-03-01 | 0 | Y |
| A110 | Mobilize site (fence, trailer, util.) | Pre-Con | GC | 10 | A100 (FS) | 2026-03-02 | 2026-03-15 | 0 | Y |
| A200 | Site clearing & demolition | Site | Demo | 15 | A110 (FS) | 2026-03-16 | 2026-04-05 | 0 | Y |
| A210 | Mass excavation | Site | Earthwork | 20 | A200 (FS) | 2026-04-06 | 2026-05-01 | 0 | Y |
| A300 | Foundation rebar & formwork | Foundation | Concrete | 15 | A210 (FS) | 2026-05-02 | 2026-05-22 | 0 | Y |
| A310 | Foundation pour + cure (28 days) | Foundation | Concrete | 28 | A300 (FS) | 2026-05-23 | 2026-06-19 | 0 | Y |
| A400 | Order long-lead steel (begin) | Pre-Con | Steel | 1 | A100 (FS) | 2026-03-02 | 2026-03-02 | 21 | N |
| A410 | Steel shop drawings + fabrication lead time (incl. shop dwg approval) | Pre-Con | Steel | 108 | A400 (FS) | 2026-03-03 | 2026-06-19 | 0 | Y |
| A500 | Structural steel erection | Structure | Steel | 25 | A310 (FS), A410 (FS) | 2026-06-20 | 2026-07-22 | 0 | Y |
| … | (continue for all activities) | … | … | … | … | … | … | … | … |
| A990 | Substantial Completion | Closeout | — | 0 | (many predecessors) | 2027-02-15 | 2027-02-15 | 0 | Y |
| A999 | Final Completion | Closeout | — | 0 | A990 (FS) + 30 | 2027-03-17 | 2027-03-17 | 0 | Y |

Relations: FS = Finish-to-Start (most common — successor cannot start until predecessor finishes); SS = Start-to-Start; FF = Finish-to-Finish; SF = Start-to-Finish (rare). Lag: "+ 30" means a 30-day lag between predecessor finish and successor start (e.g., concrete cure time). Critical?: Y = activity is on the critical path (zero float — any slip delays the project); N = activity has float and can absorb some slip without affecting the project end. Float: the number of calendar days the activity can be delayed without delaying the project end.

| Milestone | Baseline Date | Type |
| --- | --- | --- |
| Notice to Proceed | [Date] | Mandatory (contract) |
| Mobilization Complete | [Date] | Required precedent |
| Foundation Complete | [Date] | Critical path |
| Steel Topped Out | [Date] | Critical path / progress milestone |
| Building Dry-In (roof + exterior closed) | [Date] | Critical path / weather threshold |
| MEP Rough-In Complete | [Date] | Critical path |
| Drywall Complete | [Date] | Critical path |
| Finishes Complete | [Date] | Critical path |
| Commissioning Complete | [Date] | Required precedent for SC |
| Substantial Completion | [Date — per contract] | Mandatory (contract) |
| Final Completion | [Date — per contract] | Mandatory (contract) |

The 3-Week Look-Ahead is the operational schedule used at weekly trade coordination meetings. It shows what each trade is doing in the current week, the next week, and the week after that — at the trade-by-trade work-area-by-work-area level. Updated every week. Posted at the job trailer. Distributed to every trade sub PM and superintendent before each coordination meeting.

| Trade / Sub | Work Area | Week 1(Current) | Week 2(Next) | Week 3(Following) | Crew Size | Coordination Notes / Conflicts |
| --- | --- | --- | --- | --- | --- | --- |
| — SAMPLE WEEK (typical mid-construction; floor framing complete, MEP rough-in active) — |  |  |  |  |  |  |
| Concrete (Div 03)ABC Concrete | Level 4 elev. slab | Form & rebar L4 (Mon-Wed); pour Thu | Strip + cure L4 (Mon-Wed); start L5 form Thu | Rebar L5; pour Fri | 8 | Need crane priority Thu morning for L4 pour. MEP rough-in must be inspected by Wed PM. |
| Steel (Div 05)XYZ Steel | L3-L5 stairs & railings | L3 stair install (Mon-Tue); L4 rail install (Wed-Fri) | L4 stair install; L5 rail install | L5 stair install | 3 | Rail install on L4 must wait for L4 slab cure (5 days) before securing posts. |
| Mech / HVAC (Div 23)ABC Mech | L3 above-ceiling MEP rough | Hang ductwork L3 zones 1-2 | Hang ductwork L3 zone 3; start L4 | Pre-test L3 ductwork; continue L4 | 5 | L3 ceiling closure scheduled wk 4 — duct must be tested + signed off by then. |
| Plumbing (Div 22)QRS Plumbing | L3 above-ceiling rough | Above-ceiling drain & vent L3 zone 1 | Above-ceiling drain & vent L3 zones 2-3 | Pressure test L3 | 3 | Coordinate with HVAC on overhead routing — conflict at L3 column line C-7 needs resolution Mon AM. |
| Electrical (Div 26)EFG Elec | L3 above-ceiling + L2 wall rough | L3 above-ceiling conduit zones 1-2; L2 wall rough zone 3 | L3 above-ceiling zone 3; L2 wall rough zones 1-2 | L2 wall rough complete; pre-inspect | 6 | Need inspector for L2 wall rough end of wk 3 — submit inspection request by Wed wk 2. |
| Drywall (Div 09)HIJ Drywall | L1 finishing; L2 framing | Finish drywall L1 zones 1-2 (complete by Wed) | L2 wall framing zones 1-2 (Mon-Thu) | L2 wall framing zone 3; start drywall L1 zone 3 | 5 | L1 finishing held until L1 MEP rough re-inspection cleared Tue. |
| Roofing (Div 07)RoofCo | Membrane install | Membrane sections 1-2 (weather permitting) | Membrane sections 3-4 | Pre-cap inspection; start cap flashing | 4 | Weather-dependent. If rain forecast >50% Tue/Wed wk 1, hold off membrane install. |
| Painting (Div 09)PaintPro | Mobilizing | Mobilize; submittals due | Submittal review; sample mock-up | Begin L1 priming (after drywall finish complete) | 2 (mob) | Sample mock-up wk 2 — owner to attend approval. Schedule for Thu PM. |
| GC General Conditions | Site management | Crane scheduling; safety walks; coord meetings | Inspection scheduling; subcontractor billing reconciliation | Pay-app cycle; pencil draft with architect | 3 | Monthly architect pencil draft Thursday wk 3. |

Color code: green = activity scheduled to complete this week as planned · yellow = activity in progress on schedule · red = activity behind or with risk that needs attention. Coordination notes column is critical — every conflict identified in advance is a resolved meeting item; every conflict not identified is a field re-do and a delay.

Most contracts require a monthly schedule update submitted with each Application for Payment. The update reflects actual progress (% complete on each in-progress activity), forecasts revised dates for upcoming activities, and identifies impact of any change orders or delays.

Capture actuals. For each activity scheduled to be in progress or complete this period: record actual start, actual finish (if complete), and percent complete (if in progress).

Update remaining durations. For each in-progress activity: update remaining duration based on field reality (often 1.2–1.5x the original duration for activities running behind).

Recalculate forward. Run schedule recalculation. Identify which activities are now driving the new substantial completion date.

Compare to baseline. Calculate variance: revised SC date vs. baseline SC date vs. contract SC date. If variance is positive (behind), identify recovery actions.

Identify recovery options. If behind: which activities can be accelerated? Which can be re-sequenced? Where is there float that can absorb slip elsewhere?

Incorporate executed change orders. Add new CO scope as new activities; revise existing activity durations / dependencies as the CO requires.

Identify pending impacts. Pending change orders, open RFIs over 14 days, late owner-supplied items: flag potential schedule impact even if not yet quantified.

Issue updated schedule + narrative. Submit with the monthly Application for Payment: updated CPM schedule (PDF + native file format), schedule narrative explaining variance from baseline and recovery plan, updated milestone dates.

Communicate to subs. Distribute the updated 3-Week Look-Ahead reflecting any changes. Discuss in the next weekly coordination meeting.

Baseline within 30 days of NTP. The Baseline is developed in the first 30 days. Submit to architect/owner; resolve comments; freeze as the contract baseline. Schedules that don't get baselined never get used.

Long-lead items identified day 1. Within the first week of NTP, every long-lead procurement (steel, custom curtain wall, custom switchgear, custom MEP equipment, custom millwork, specialty AV) is on the schedule with the lead time as a real activity, not a footnote.

Every activity has a responsible party. The schedule activity list assigns a responsible trade or sub for every line item — no orphan activities.

Critical path identified and visible. Every monthly schedule update highlights the current critical path. Activities on the critical path get extra scrutiny in coordination meetings.

Float belongs to the project, not to the trade. Float is a project resource — when one trade slips into another's float, both share the float. Don't let early trades consume all the float and leave later trades zero buffer.

Look-Ahead updated weekly, period. Every Monday before noon, the Look-Ahead reflects Friday-actuals and is distributed to every sub. Don't skip weeks. Don't merge weeks.

Weekly coordination meeting walks the Look-Ahead. The meeting agenda is the Look-Ahead — row by row, each sub confirms or flags conflicts. Meetings without the Look-Ahead in front of every attendee become rambling chat sessions.

Inspector and architect attendance scheduled in the Look-Ahead. Inspections, architect site visits, owner walks — schedule them on the Look-Ahead so they don't become last-minute scrambles.

Weather-sensitive activities flagged. Roofing, exterior masonry, asphalt paving, concrete pour in cold weather — flag in the Look-Ahead with the weather contingency.

Schedule narrative submitted monthly. Plain-English 1–2 page narrative with the schedule update. Variance, critical path, recovery plan.

Time extensions documented as they occur. When a delay event occurs (owner change, weather, late owner-supplied item, late RFI response), document the date, cause, and projected schedule impact. Submit time-extension request within the contract notice period (typically 7–14 days) — late requests are deemed waived.

Recovery schedule when behind by 10+ days. If cumulative variance reaches 10 days behind baseline SC, issue a recovery schedule showing what acceleration is required and at what cost. Owner-decision-required: accept the slip, or fund the acceleration. Don't silently absorb 30 days of slip with no plan.

Document version: 2026-05-15 (v1.0). Industry-standard CPM and short-interval scheduling practices. Maintained as part of the ContrPro Complete tier — General Contractor suite.