## Instructions
BOLT INSPECTION LOG — Instructions
WHAT THIS WORKBOOK IS
Daily record-keeping companion to the Bolt Installation & Inspection Guide HTML. Captures the documentation the special inspector (and any post-completion forensic) will demand: bolt lot metadata, pre-installation Skidmore verification, per-connection install records, and a daily roll-up.
WORKFLOW — ONE-TIME SETUP
1. Project Info: project, GC, erector, special inspector, Skidmore serial.
2. Bolt Lot Master: one row per bolt lot received from the fabricator/supplier. MTR # is the key — it must match the paperwork from the supplier and must be on file before any bolt from that lot is installed.
WORKFLOW — DAILY
1. First thing each shift, perform Skidmore pre-installation verification per RCSC §7.
2. Log the verification on Pre-Installation Verification Log. Three bolt-nut-washer assemblies from each active lot, all reading ≥ 105% of RCSC Table 8.1 minimum pretension.
3. As bolts are installed during the shift, log each connection on Connection Log (location, method used, bolt lot, count, installer, status).
4. After installation, mark installed bolts (typically with a paint slash from bolt head to ply) so missed bolts are visually obvious to the special inspector.
5. Inspector verifies installation — logs sign-off on Connection Log.
6. End of shift: Daily Roll-Up tab auto-aggregates totals.
RCSC TABLE 8.1 — MINIMUM PRETENSION (REFERENCE)
3/4" A325: 28 kips 7/8" A325: 39 kips 1" A325: 51 kips
3/4" A490: 35 kips 7/8" A490: 49 kips 1" A490: 64 kips
See the Bolt Lot Master tab for full table by size + grade.
Skidmore target = 105% of these minimums.
INSPECTION SAMPLING (RCSC §9.2.2 / Table 9.2)
Slip-critical and fatigue-loaded: 100% routine observation during installation.
Standard pretensioned: reduced sampling per Special Inspector's program (typically 10-25%).
Snug-tight: visual only — no pretension verification required.
MARKING CONVENTION
Standard color marking on installed-and-inspected bolts:
- Yellow paint slash = installed, awaiting inspection
- Green paint slash = installed + inspected, accepted
- Red paint slash = rejected — bolt to be replaced
Use the convention agreed with the special inspector at the pre-erection meeting.
RETENTION
Retain this workbook + all MTRs + Skidmore calibration certificate + Special Inspector reports for the project life PLUS the state's statute of repose for construction defect claims (typically 6-10 years post-substantial completion).

## Project Info
BOLT INSPECTION PROJECT INFO
Project Name
Project Address
Owner
Controlling Contractor (GC)
Steel Erector
Fabricator
Special Inspection Agency (SAA)
Lead Special Inspector (AWS CWI #)
EOR
Skidmore-Wilhelm serial #
Skidmore calibration certificate date
Skidmore calibration expiration
Project Quality Manager (Sub)
Erection start date
Anticipated bolt installation completion

## Reference (hidden)
RCSC Table 8.1 — Min Pretension (kips)
Size | Grade | Min Pretension (kips)
1/2 | A325 | 12
5/8 | A325 | 19
3/4 | A325 | 28
7/8 | A325 | 39
1 | A325 | 51
1-1/8 | A325 | 56
1-1/4 | A325 | 71
1-3/8 | A325 | 85
1-1/2 | A325 | 103
1/2 | A490 | 15
5/8 | A490 | 24
3/4 | A490 | 35
7/8 | A490 | 49
1 | A490 | 64
1-1/8 | A490 | 80
1-1/4 | A490 | 102
1-3/8 | A490 | 121
1-1/2 | A490 | 148

## Bolt Lot Master
BOLT LOT MASTER
One row per bolt lot received. RCSC minimum pretension auto-fills based on size + grade — Skidmore target is 105% of that minimum.
Lot # | Bolt Size | Grade | Length (in) | Finish | Manufacturer | MTR / Cert # | Date Received | RCSC Min Pretension (kips) | Skidmore Target (105% kips) | Pre-Install Verified? | Last Verification Date | Quantity Received | Quantity Installed | Notes

## Pre-Install Verification
PRE-INSTALLATION VERIFICATION LOG
RCSC §7. Test 3 bolt-nut-washer assemblies from each active lot at start of shift OR when anything changes. All 3 readings must meet or exceed the 105% target.
Date | Time | Lot # | Bolt Size | Grade | Method | Test #1 Pretension (kips) | Test #2 Pretension (kips) | Test #3 Pretension (kips) | Target (105% min) | Pass / Fail | Ironworker | Inspector | Notes

## Connection Log
CONNECTION INSTALLATION + INSPECTION LOG
One row per connection. Status auto-rolls: Snug → Tightened → Inspected → Accepted / Rejected. Slip-critical column N is only relevant for SC connections — verify faying surface class.
Date | Connection ID | Location (Gridline/Floor) | Connection Type | Method | Lot # | # Bolts | Installer / Crew | Snug-Tight Complete | Final Tighten Complete | Marked (color) | Inspector Sign-Off | Status | Slip-Critical Faying OK? | Notes
TOTALS

## Daily Roll-Up
DAILY ROLL-UP — Bolt Installation Status
Auto-aggregated from Connection Log. Use for daily progress reporting + monthly billing back-up.
Total connections logged
Total bolts installed
Connections — Pending
Connections — Snug-Tight only
Connections — Awaiting Inspection
Connections — Accepted
Connections — Rejected
Connections — Re-inspect
By Connection Type
Snug-Tight type connections
Pretensioned type connections
Slip-Critical type connections
By Method
Turn-of-Nut
Calibrated Wrench
Twist-Off (TC)
DTI Washer
Skidmore verifications logged
Skidmore verifications PASSED
Skidmore verifications FAILED