## Instructions
STEEL ERECTION BID ESTIMATOR — Instructions
WHAT THIS WORKBOOK IS
A tonnage-based bid estimator for a structural-steel erection subcontractor. Output is a final bid number broken down by CSI division and section, suitable for submitting on a commercial bid form (use the Bid Package & Prequalification template from the Universal Sub Suite for the wrapper).
WORKFLOW (TYPICAL BID DAY)
1. Open the bid documents and identify the structural drawings (S-series sheets) + project manual (Division 05 specifications).
2. Project Info: fill in the project, GC, delivery method, schedule, location, prevailing-wage flag, and contract-type assumptions. These drive every other tab.
3. Wage Rates: review the defaults against the locality + project labor regime. On Davis-Bacon or state-prevailing-wage projects, REPLACE the defaults with the controlling wage determination (see Certified Payroll Tracker for parallel workflow).
4. Equipment Rates: replace defaults with quotes from your crane vendor for the project tonnage + reach + pick weight. The 200T crawler default is a sample; bigger projects need bigger cranes.
5. Material Takeoff: enter the tonnage / sqft / count by CSI section. The takeoff usually comes from a quantity surveyor's report, a fabricator's takeoff (if you bid as erector-only), or your own takeoff from the structural drawings.
6. Labor Estimate: apply productivity rates (hrs/ton) by member class and crew composition. Industry-average productivity rates are pre-loaded; tighten or relax based on project access, complexity, weather window, etc.
7. Equipment Estimate: estimate crane-days and support-equipment days by phase.
8. Subcontract Estimate: if any scope is subbed (high-strength bolting, certified welding, fireproofing, painting), price as lump-sum or unit-price.
9. Premiums & Conditions: apply percentage adders for working at heights, after-hours work, distance from your shop, complex geometry, weather contingency, and similar risk factors.
10. Bid Summary: review the CSI-division roll-up. Apply contingency, bond cost, overhead, and profit to arrive at the final bid number.
WHAT THIS WORKBOOK IS NOT
- This is not a substitute for a takeoff. Garbage in, garbage out — the bid is only as good as the tonnage entered.
- This is not a substitute for a contract review. The Subcontract Review Checklist (Universal Sub Suite) is for the deal terms; this estimator is for the price only.
- This is not a substitute for an erector's experience. The pre-loaded productivity rates are industry averages; your shop's actual productivity may be 20-40% different. Calibrate against your last 3 completed jobs before relying on the rates on a tight bid.
CSI MASTERFORMAT INTEGRATION
Every line item carries a CSI Division (05 primary for steel) and Section (e.g., 05 12 23 Structural Steel Framing, 05 31 13 Steel Floor Decking). The Bid Summary tab rolls up totals by CSI division so the bid integrates cleanly into the GC's job-cost accounting and into your monthly Sub Schedule of Values billing.
STEEL ERECTOR'S SCOPE — TYPICAL DIVISIONS
- 05 12 23 Structural Steel Framing — primary structural members (W, HSS, C, L)
- 05 21 19 Open-Web Steel Joists — K, LH, DLH series
- 05 31 13/23/33 Steel Decking — floor / roof / form decking
- 05 50 00 Metal Fabrications — misc metals, embeds, railings (sometimes)
- 05 51 13 Metal Pan Stairs — stairs installed by erector
- 03 30 00 (cross-ref) — embed plates supplied by erector, set by concrete contractor
- 07 81 00 (cross-ref) — spray-applied fireproofing, typically a separate sub
PRODUCTIVITY RATES (DEFAULTS — ADJUST BASED ON YOUR HISTORY)
- Structural steel: 8-15 tons/crew-day for normal commercial work; 4-8 for AESS or congested
- Joists: 25-45 joists/crew-day depending on span and bridging
- Decking: 7,000-12,000 sqft/crew-day on open floors, less on cut-up plans
- Bolting: 80-150 high-strength bolts/bolter-day (turn-of-nut method)
- Welding: depends entirely on weld size and position — estimate per joint, not per ton
MARKUP DEFAULTS (REVIEW PER PROJECT)
- Overhead: 12-18% on commercial work
- Profit: 8-12%
- Contingency: 3-5% (more for design-build, less for fully-detailed bid)
- Bond: 0.5-1.5% of bid
- Total all-in markup typically lands at 25-35% above raw cost
FIELD-ONLY SCOPE (CONTRPRO STEEL ERECTION TRADE PACK SCOPE)
This estimator is calibrated for FIELD ERECTION only. Fabrication shop work is OUT OF SCOPE — if your firm fabricates AND erects, use a separate fabrication-shop estimator (different rate structure, different productivity, different material handling).

## Project Info
PROJECT INFORMATION — Steel Erection Bid
Project Name
Project Address
Owner
General Contractor (bidding to)
Bid Due Date
Project Type | Commercial — New Construction
Delivery Method | Design-Bid-Build
Construction Schedule (months) | 0
Anticipated Steel Erection Start
Anticipated Steel Erection Duration (weeks) | 0
LABOR REGIME
Davis-Bacon / Prevailing Wage Project? | No
Wage Determination ID (if prevailing wage)
Union Project? | No
Project State (controls workers' comp + EMR application)
BID ECONOMICS
Fringe Burden % (on bare wage) | 40%
OT Premium Multiplier | 1.5
Labor Overhead % | 15%
Labor Profit % | 10%
Material Markup % | 10%
Equipment Markup % (rented) | 8%
Equipment Markup % (owned) | 10%
Subcontract Markup % | 7%
Project Contingency % | 4%
Bond % of Bid | 1.2%
Project-Level Overhead % | 13%
Profit % | 10%
KEY PROJECT ATTRIBUTES
Maximum Working Height (ft) | 0
Heights >50ft Premium Trigger? | No
After-Hours / Weekend Work Required? | No
Distance from Shop (miles) | 0
AESS (Architecturally Exposed Steel)? | No
Complex Geometry (curved, slanted, offsets)? | No
Site Access Constraints (urban, occupied, phased)? | No
PRINCIPAL / BIDDER OF RECORD
Estimator
Project Executive (Sub)
Authorized Signatory

## Wage Rates
WAGE RATES — Ironworker Classifications
Bare wage = pre-burden hourly rate. Burdened = bare × (1 + FringeBurden). Billed = burdened × (1 + LaborOH) × (1 + LaborProfit). On prevailing-wage / Davis-Bacon projects, replace bare wage with the wage determination base rate; fringe is paid in cash or to a bona-fide plan.
Classification | Bare Wage ($/hr) | OT Multiplier | Burdened ST ($/hr) | Burdened OT ($/hr) | Billed ST ($/hr) | Billed OT ($/hr) | Notes
Foreman / Working Foreman | 58 | 1.5
Journeyman Ironworker — Structural | 46 | 1.5
Journeyman Ironworker — Connector | 48 | 1.5
Journeyman Ironworker — Welder (Certified) | 52 | 1.5
Apprentice Ironworker — Year 4 | 36 | 1.5
Apprentice Ironworker — Year 3 | 32 | 1.5
Apprentice Ironworker — Year 2 | 28 | 1.5
Apprentice Ironworker — Year 1 | 24 | 1.5
Crane Operator | 54 | 1.5
Signal Person / Rigger | 44 | 1.5
Decker / Bolter | 42 | 1.5
Detailer (field) | 50 | 1
Field Engineer / Surveyor | 56 | 1

## Equipment Rates
EQUIPMENT RATES
Owned equipment: bare cost + internal markup. Rented: rental rate + small markup for handling. For project-specific bids, replace rental defaults with actual quotes from your crane vendor.
Equipment | Owned / Rented | Hourly Rate ($) | Daily Rate ($) | Weekly Rate ($) | Markup % | Billed Daily ($) | Billed Weekly ($) | Notes
Crawler crane — 80T | Rented | 185 | 1850 | 7400
Crawler crane — 110T | Rented | 235 | 2350 | 9400
Crawler crane — 150T | Rented | 310 | 3100 | 12400
Crawler crane — 200T | Rented | 395 | 3950 | 15800
Truck-mounted crane — 50T (RT) | Rented | 165 | 1650 | 6600
Truck-mounted crane — 80T (RT) | Rented | 220 | 2200 | 8800
Boom truck — 18T (carrydeck) | Owned | 95 | 950 | 3800
Telehandler / forklift | Owned | 72 | 720 | 2880
Aerial lift — scissor 26'-32' | Rented | 48 | 480 | 1920
Aerial lift — boom 60'-85' | Rented | 98 | 980 | 3920
Engine-drive welder (lincoln/miller) | Owned | 18 | 180 | 720
Air compressor — 185 cfm | Owned | 14 | 140 | 560
Generator — 25 kW | Owned | 12 | 120 | 480

## Material Takeoff
MATERIAL TAKEOFF — CSI-Coded
Enter one row per CSI-coded material/system. UOM examples: TON (structural steel), EA (joists), SF (decking), LF (railings), LB (bolts), GAL (paint). Materials supplied by erector — if the fabricator supplies material direct, exclude from this tab and note in Assumptions.
Line # | CSI Section | Description | UOM | Quantity | Unit Cost ($) | Material Subtotal ($) | Markup % | Material Total ($) | Notes
| 05 12 23 | Structural Steel — Wide Flange (W shapes) | TON
| 05 12 23 | Structural Steel — HSS / Pipe | TON
| 05 12 23 | Structural Steel — Channels / Angles / MC | TON
| 05 12 23 | Structural Steel — Plate / Bent Plate | TON
| 05 12 33 | AESS — Architecturally Exposed Steel (premium) | TON
| 05 12 23 | High-Strength Bolts — A325 (3/4" ASTM F3125) | EA
| 05 12 23 | High-Strength Bolts — A325 (7/8" ASTM F3125) | EA
| 05 12 23 | High-Strength Bolts — A490 (1" ASTM F3125) | EA
| 05 12 23 | Tension-Control Bolts — F1852 / F2280 | EA
| 05 12 23 | Anchor Rods — F1554 Grade 36 | EA
| 05 21 19 | Open-Web Steel Joists — K-Series | EA
| 05 21 19 | Open-Web Steel Joists — LH-Series | EA
| 05 21 23 | Joist Girders | EA
| 05 31 13 | Steel Floor Deck — 1.5VL Composite | SF
| 05 31 13 | Steel Floor Deck — 2VL Composite | SF
| 05 31 13 | Steel Floor Deck — 3VL Composite | SF
| 05 31 13 | Shear Studs — 3/4" × 4-1/2" Headed | EA
| 05 31 23 | Steel Roof Deck — 1.5B Wide-Rib | SF
| 05 31 23 | Steel Roof Deck — 1.5BR Wide-Rib Acoustic | SF
| 05 31 23 | Steel Roof Deck — 3B Long-Span | SF
| 05 50 00 | Misc Metals — Embed Plates | EA
| 05 50 00 | Misc Metals — Lintels | LF
| 05 51 13 | Metal Pan Stairs — Risers | EA
| 05 51 13 | Stair Stringers / Landings | EA
| 05 52 13 | Pipe Railings — Stair Rail | LF
| 05 52 13 | Pipe Railings — Roof Edge / Platform | LF
| 09 91 00 | Touch-Up Primer (welds + abrasions) | GAL
MATERIAL TOTAL

## Labor Estimate
LABOR ESTIMATE — Productivity × Crew × Rate
Productivity = crew-hours per unit of work (e.g., 3.50 crew-hrs/ton = a 5-person crew working an 8-hour day erects roughly 11.5 tons/day). Pull quantities from Material Takeoff. Avg Crew Rate is the loaded (burdened + marked-up) blended hourly rate across the crew composition.
⚠ CALIBRATE AGAINST YOUR LAST 3 COMPLETED JOBS BEFORE TRUSTING THESE NUMBERS. Defaults are commercial-South non-union industry averages. Union work, cold climates, AESS, or congested sites typically run 20-40% slower.
Activity | CSI Section | Quantity | UOM | Productivity (hrs/UOM) | Crew Composition (#) | Total Labor Hours | Avg Crew Rate ($/hr) | Labor Total ($) | Notes
Erect structural steel — typical | 05 12 23 |  | TON | 3.5 | 5 |  | 46
Erect structural steel — AESS (premium) | 05 12 33 |  | TON | 6.5 | 5 |  | 46
Erect open-web joists | 05 21 19 |  | EA | 0.4 | 4 |  | 44
Erect joist girders | 05 21 23 |  | EA | 1.5 | 4 |  | 46
Install floor decking | 05 31 13 |  | SF | 0.02 | 4 |  | 42
Install roof decking | 05 31 23 |  | SF | 0.018 | 4 |  | 42
Install shear studs (Nelson-stud welding) | 05 31 13 |  | EA | 0.08 | 2 |  | 48
Set / shim embeds and base plates | 05 12 23 |  | EA | 0.5 | 2 |  | 44
Install misc metals (embeds, lintels) | 05 50 00 |  | EA | 1 | 2 |  | 44
Install metal pan stairs (per riser) | 05 51 13 |  | EA | 0.6 | 3 |  | 46
Install pipe railings | 05 52 13 |  | LF | 0.3 | 2 |  | 42
Bolt-up (high-strength, turn-of-nut) | 05 12 23 |  | EA | 0.08 | 2 |  | 42
Field welding (per joint) | 05 12 23 |  | EA | 0.35 | 2 |  | 52
Touch-up primer (after erection) | 09 91 00 |  | GAL | 0.5 | 1 |  | 42
Plumb-and-true survey (per bay) | 05 12 23 |  | EA | 0.75 | 2 |  | 50
Final cleanup / demobilization | 05 12 23 |  | DAY | 8 | 4 |  | 42
LABOR TOTAL

## Equipment Estimate
EQUIPMENT ESTIMATE
Days = total billable days on the project. Crane phase typically = structural steel + joists + girders + decking days. Some equipment (welder, generator) runs the full erection duration.
Equipment | Phase / Activity | Days | Daily Rate ($) | Subtotal ($) | Markup % | Total ($) | Notes
Primary crane (e.g., 150T crawler) | Steel + joists + decking |  | 3100
Secondary crane (e.g., 80T) | Misc lifts / overflow |  | 1850
Boom truck / carrydeck | Bolt-up + misc |  | 950
Aerial lift — boom 60-85' | Connection / welding |  | 980
Aerial lift — scissor | Decking / detailing |  | 480
Engine-drive welder | Field welding |  | 180
Telehandler / forklift | Material handling |  | 720
Air compressor | Bolting / impact |  | 140
Generator | Power for tools |  | 120
Mobilization / demobilization (allowance) | Each crane move |  | 0
0
EQUIPMENT TOTAL

## Subcontract Estimate
SUBCONTRACT ESTIMATE — Lower-Tier Work
Scopes commonly subbed by a steel erector: high-strength bolting, certified welding, spray-applied fireproofing, painting/galvanizing touch-up, decking install (if not self-performed). Get firm quotes from the lower-tier sub before bid day; lump-sum or unit-price.
Scope | CSI Section | Sub Quote ($) | Markup % | Total ($) | Sub Name | Notes
High-strength bolting (TC bolts, calibrated wrench) | 05 12 23
Certified welding (AWS D1.1 structural) | 05 12 23
Spray-applied fireproofing (SFRM) | 07 81 00
Touch-up primer / paint | 09 91 00
Galvanizing repair (cold-galv compound) | 05 12 23
Decking install (if not self-performed) | 05 31 13
Bolt inspection (third-party) | 05 12 23
Welding inspection (third-party UT/MT/PT) | 05 12 23
SUBCONTRACT TOTAL

## Premiums & Conditions
PREMIUMS & CONDITIONS — Risk Adders
Percentage adders applied to the base labor + equipment + subcontract subtotal. Use when a project attribute materially increases productivity loss, risk, or carrying cost.
Condition | Applies? | Premium % | Basis / Notes
Working at heights >50 ft (OSHA 1926.760 fall protection) |  | 7% | Productivity loss, equipment for fall protection
After-hours / weekend / night work (shift premium) |  | 15% | 1.5× OT or shift differential
Distance from shop >50 miles |  | 4% | Per-diem, travel time, equipment-move cost
Architecturally Exposed Steel (AESS — Tier 2 or higher) |  | 12% | Slower productivity, higher tolerance, more handling
Complex geometry (curved, slanted, twisted, offsets) |  | 10% | Slower placement, more shimming, more rework
Constrained site (urban, occupied, phased, tight crane swing) |  | 8% | Slower productivity + more crane positions
Winter weather (Nov-Mar in cold climates) | No | 6% | Lost days, equipment heating, ice/snow removal
Hurricane / wind contingency (coastal projects) | No | 3% | Stoppage during named storms, anchor verification
Davis-Bacon / state prevailing wage |  | 0% | Already captured in wage rates — informational
Project-specific PPE (FR, arc-flash, special tie-off) | No | 1% | PPE replacement frequency
0%
0%
TOTAL PREMIUM % (applied to labor + equip + sub)

## Bid Summary
BID SUMMARY — Roll-Up to Final Bid
Project: =ProjectName GC: =GCName
DIRECT COST ROLL-UP
Material (from Material Takeoff)
Labor (from Labor Estimate)
Equipment (from Equipment Estimate)
Subcontract (from Subcontract Estimate)
DIRECT COST SUBTOTAL
Premium (heights, after-hours, distance, AESS, etc.)
COST OF WORK SUBTOTAL
Contingency
Project Overhead (general conditions, supervision)
Profit
BID BEFORE BOND
Performance + Payment Bond |  |  | Of final bid
FINAL BID NUMBER
SANITY CHECKS
$/Ton (final bid / total structural tons)
$/SF Decking (subcontract + decking labor)
Labor % of final bid (sanity: typically 25-45%)
Equipment % of final bid (sanity: typically 8-18%)
Markup % effective (above raw direct cost)
CSI DIVISION ROLL-UP (for Sub Schedule of Values)
CSI Division | Material ($) | Labor ($) | Total ($)
03 — Cast-in-Place Concrete (embeds cross-ref)
05 — Metals
07 — Thermal & Moisture (fireproofing cross-ref)
09 — Finishes (paint cross-ref)

## CSI Reference (hidden)
CSI MasterFormat — Steel Erector Scope
Section | Title | Scope Notes
05 12 23 | Structural Steel Framing | Primary structural steel members (W, HSS, C, L, MC shapes)
05 12 33 | Architecturally Exposed Structural Steel (AESS) | AESS tier finish steel — higher tolerance, more prep
05 21 19 | Open-Web Steel Joists | K-series, LH-series, DLH-series joists
05 21 23 | Joist Girders | Long-span joist girders supporting joists
05 31 13 | Steel Floor Decking | Composite or non-composite floor deck (1.5VL, 2VL, 3VL, etc.)
05 31 23 | Steel Roof Decking | Roof deck (1.5B, 2B, 3B, 1.5BR, etc.)
05 31 33 | Steel Form Decking | Permanent metal form decking
05 41 00 | Structural Metal Stud Framing | Load-bearing metal stud framing (rare for erector)
05 50 00 | Metal Fabrications | Miscellaneous metals — railings, ladders, embed plates
05 51 13 | Metal Pan Stairs | Metal pan stairs installed by erector
05 51 33 | Metal Ladders | Caged/uncaged metal ladders
05 52 13 | Pipe and Tube Railings | Stair, balcony, and platform railings
05 71 13 | Fabricated Metal Spiral Stairs | Spiral stairs (often shop-fab + field erect)
05 73 16 | Wire Rope Decorative Metal Railings | Tension wire-rope cable rail systems
03 30 00 | Cast-in-Place Concrete (embeds) | Embed plates / anchor rods — supplied by erector, set by concrete contractor
05 75 00 | Decorative Formed Metal | Decorative cladding / canopies
07 81 00 | Applied Fireproofing | Spray-applied fireproofing on steel (typically separate sub)
09 91 00 | Painting (Touch-Up) | Shop primer touch-up on welds/abrasions
13 34 19 | Pre-Engineered Metal Buildings | PEMB — if erector takes on the metal-building scope
33 16 00 | Water Utility Storage Tanks (Steel) | Bolted/welded steel water tanks