The Pre-Erection Meeting ("PEM" or "MEC" — Multi-Employer Coordination) is the single most important coordination event in a steel-erection project. AISC Code of Standard Practice §4.3 and 29 CFR 1926.752 both contemplate a documented pre-erection meeting between the steel erector, the controlling contractor, the EOR, the fabricator, and adjacent-trade subs. Use this checklist as both the meeting agenda AND the meeting minutes. Sign at the end. File a signed copy in the project record and post a copy at the jobsite trailer. Most steel-erection disputes — change-order rejections, schedule disputes, safety citations — can be traced to a meeting item that was skipped or never documented.

Section 1 — Attendance Roster

Section 2 — Project Identification & Schedule

Section 3 — §1926.752(a) Notification Status

Section 4 — Site-Specific Erection Plan (SSEP) Review

Section 5 — Crane Operations & Lift Plan

Section 6 — Erection Sequence & Concurrent Trades

Section 7 — Fall Protection Responsibility Matrix

Section 8 — Site Utilities, Energized Lines, & De-Energization

Section 9 — Submittals, RFIs, Mill Certs, & Material Tracking

Section 10 — Insurance, COIs, & Indemnity Confirmation

Section 11 — Emergency Response & Communications

Section 12 — Weather, Stop-Work, & Site Shutdown Criteria

Section 13 — Day 1 Logistics & First-Lift Plan

Section 14 — Action Items & Open Issues

Section 15 — Signatures & Distribution

The following attendees are required for a documented pre-erection meeting. Substitutes must be authorized in writing. Each attendee signs the attendance roster on arrival and the document at Section 15 at adjournment.

| Role | Required? | Name | Firm | Phone | Email | Present? |
| --- | --- | --- | --- | --- | --- | --- |
| Steel Erector PM | Required | [Name] | [Firm] | [Phone] | [Email] | ☐ |
| Steel Erector Site Super | Required | [Name] | [Firm] | [Phone] | [Email] | ☐ |
| Steel Erector Foreman | Required | [Name] | [Firm] | [Phone] | [Email] | ☐ |
| Steel Erector Safety Officer | Required | [Name] | [Firm] | [Phone] | [Email] | ☐ |
| Controlling Contractor PM | Required | [Name] | [GC] | [Phone] | [Email] | ☐ |
| Controlling Contractor Super | Required | [Name] | [GC] | [Phone] | [Email] | ☐ |
| Controlling Contractor Safety | Required | [Name] | [GC] | [Phone] | [Email] | ☐ |
| Structural EOR rep | Highly recommended | [Name] | [EOR firm] | [Phone] | [Email] | ☐ |
| Fabricator rep | Recommended | [Name] | [Fab] | [Phone] | [Email] | ☐ |
| Crane vendor / Lift Director | Required if non-erector crane | [Name] | [Vendor] | [Phone] | [Email] | ☐ |
| Concrete sub (foundation/embeds) | Required first PEM | [Name] | [Sub] | [Phone] | [Email] | ☐ |
| Decking sub (if separate) | If applicable | [Name] | [Sub] | [Phone] | [Email] | ☐ |
| Fireproofing sub (if separate) | If applicable | [Name] | [Sub] | [Phone] | [Email] | ☐ |
| MEP coordinator (if concurrent) | If concurrent in bays | [Name] | [Firm] | [Phone] | [Email] | ☐ |
| Owner's rep / CM | Recommended | [Name] | [Firm] | [Phone] | [Email] | ☐ |

| Project Name: | [Project Name] |
| --- | --- |
| Project Address: | [Street, City, State] |
| Owner: | [Owner Legal Name] |
| Controlling Contractor: | [GC] |
| Steel Erector Subcontract No.: | [Subcontract #] |
| Total Steel Tonnage: | [Tons] |
| Anticipated Erection Duration: | [Weeks] |
| First Steel Delivery Date: | [Date] |
| First Steel Erection Day: | [Date] |
| Anticipated Topping-Out Date: | [Date] |
| Anticipated Steel Demobilization: | [Date] |
| Anticipated Substantial Completion (overall project): | [Date] |

[Foundation cure dates, MEP rough-in cutover, weather windows, owner-driven milestones, tower-crane jumps, etc.]

| Concrete strength notification received: | ☐ Yes — date[Date]☐ Pending — expected[Date] |
| --- | --- |
| Notification format: | ☐ Written letter ☐ Email with cylinder break data ☐ Other:[Format] |
| Required design strength: | [psi] |
| 75% threshold: | [psi] |
| Actual cylinder break results: | [psi at age N days — by test lab] |
| Anchor-rod survey received: | ☐ Yes ☐ Pending ☐ N/A |
| Anchor-rod variances: | ☐ None ☐ Documented + EOR-approved field memo attached |
| Anchor-rod stickup & pattern verified by survey: | ☐ Yes — surveyor:[Name + cert] |

Decision recorded: Steel erection [may begin / shall not begin until item X is resolved] on [Date].

| SSEP version reviewed in this meeting: | [v# / Date] |
| --- | --- |
| SSEP distributed to all attendees: | ☐ Yes ☐ Walked through during meeting |
| SSEP-required action items by Controlling Contractor: | [List] |
| SSEP-required action items by other subs: | [List] |
| SSEP revision triggered by this meeting? | ☐ No ☐ Yes — see Section 14 (Action Items) |

Discussion notes: [Key points raised — sequence concerns, equipment, fall protection]

| Primary crane operator: | [Name — NCCCO/State # — Exp] |
| --- | --- |
| Backup crane operator: | [Name — Cert] |
| Lift Director (1926.1432(b)): | [Name — designated in writing] |
| Signal Person(s) (1926.1428): | [Names — qualifications on file] |
| Annual crane inspection (1926.1412(f)): | ☐ Current — date[Date] |
| Daily crane inspection (1926.1412(d)): | ☐ Procedure agreed; documented on Daily Field Report |
| Crane medical fitness (1926.1427(j)): | ☐ All operators current |

| Anticipated critical lifts on this project: | [#] |
| --- | --- |
| Critical Lift Plans drafted: | ☐ Yes — seeCritical_Lift_Calculator.xlsx☐ Pending |
| EOR review of critical lifts over occupied structure: | ☐ Yes — date[Date]☐ N/A |
| Tandem lifts planned: | ☐ No ☐ Yes — separate plan required |
| Personnel-platform ("man basket") lifts (1926.1431): | ☐ No ☐ Yes — separate plan + practical demonstration required |

Crane positions, travel paths, swing-radii, and exclusion zones are documented on the SSEP Exhibit A site plan, reviewed in this meeting and accepted by all attendees. Material lay-down areas confirmed.

SSEP Section 3 sequence reviewed. Concurrent-trade coordination items discussed:

| Trade | Where in sequence | Coordination Required | Owner |
| --- | --- | --- | --- |
| Concrete (foundations/embeds) | Pre-erection + ongoing | Embed plate set, anchor rod tolerance, base-plate grout | [GC/Concrete sub] |
| Masonry | Concurrent with steel (in some sequences) | Crane swing exclusion, mason scaffold proximity | [GC] |
| MEP rough-in | After bay erected + decked | Bay handover timing, fall protection on decked floors | [GC + MEP coordinator] |
| Decking (if separate) | Following structural steel | Bay handover, weld pin / power-fastener authority | [Decking sub] |
| Fireproofing | After decking, before MEP closeout | Bay handover, overspray protection, deck embed cleanup | [Fireproofing sub] |
| Painting (touch-up) | After erection, before finishes | Weld grind, primer touch-up scope split | [Paint sub] |
| Roofing | After roof deck | Roof-deck attachment standards, perimeter cable handover | [Roofing sub] |
| Curtainwall / cladding | After plumb-and-true signed off | Edge of slab tolerance, embed verification for anchors | [Curtainwall sub] |

Per OSHA Multi-Employer Citation Policy, fall-protection responsibility must be clearly assigned. The matrix below is reviewed and accepted by the controlling contractor, the steel erector, and each downstream sub at this meeting.

| System / Location | Installer | Maintainer During Steel Erection | Handover Trigger | Maintainer After Handover |
| --- | --- | --- | --- | --- |
| PFAS anchor points on steel | Erector (engineered) | Erector | Substantial completion of steel | Erector / GC (jointly until demob) |
| Perimeter cable / guardrail (open edges) | [Erector / GC] | [Erector / GC] | [Bay handover] | [GC] |
| Floor-hole covers + skylight protection | [GC / Trade installing the opening] | GC | Hole created | GC throughout |
| Stairs & landings (during install) | Erector | Erector | Final attachment + handrail | GC |
| Internal floor edges (atrium, openings) | [Erector / GC] | GC | Decking complete | GC |
| Wall openings (curtainwall reveals) | GC | GC | N/A | GC |

| Overhead power lines within crane swing radius: | ☐ None ☐ Present — see plan |
| --- | --- |
| Highest line voltage: | [V] |
| Minimum clearance per §1926.1408 Table A: | [ft — by voltage] |
| De-energization plan: | ☐ Lines de-energized by utility ☐ Insulating lines or barriers ☐ Spotter (1926.1408(c)) ☐ Other engineered method |
| Utility company contact: | [Name + 24h phone] |
| Pre-job utility ticket (811): | ☐ Filed — ticket #[#] |
| Underground utility markings refreshed within 21 days: | ☐ Yes |
| Adjacent live MEP (energized panels, gas, fuel): | [Description + isolation plan] |

| Shop drawings approved: | ☐ All approved — date[Date]☐ Partial — see RFI log |
| --- | --- |
| Erection drawings (E-series) issued: | ☐ Yes — version[Rev / Date] |
| Mill test reports (MTRs) chain of custody: | ☐ Fabricator providing per heat lot — agreed |
| Bolt certification (RCSC / ASTM F3125): | ☐ Mill certs + manufacturer's certs supplied with each lot |
| Welding Procedure Specifications (WPS): | ☐ AWS D1.1 compliant — on file at jobsite |
| Welder qualification records (WQR): | ☐ Current — all field welders qualified for assigned positions |
| Material delivery sequence: | [Phase-aligned per delivery schedule attached] |
| Material lay-down ownership: | [Erector / GC] |
| Material damage / replacement protocol: | [Document on Daily Field Report; replacement turnaround] |
| RFI turnaround SLA: | [# business days] |

| Steel erector COI on file with GC: | ☐ Yes — date[Date] |
| --- | --- |
| Additional Insured (Owner + GC): | ☐ CG 20 10 + CG 20 37 endorsements confirmed |
| Primary & non-contributory: | ☐ Yes |
| Waiver of subrogation: | ☐ Yes — applicable lines |
| Limits match Subcontract: | ☐ CGL[$ per occ / agg]☐ Excess[$]☐ Auto[$]☐ WC statutory |
| Builder's Risk policy in place: | ☐ Owner-supplied ☐ GC-supplied ☐ Sub deductible:[$] |
| Crane operator insurance + crane policy verified: | ☐ Yes |
| Indemnity provisions of Subcontract Article 8: | Reviewed; comparative-negligence form per state anti-indemnity statute |

| Nearest hospital w/ trauma capability: | [Name + address + phone + ETA from site] |
| --- | --- |
| Site assembly point (evacuation): | [Location] |
| First-aid responder on site: | [Name + cert] |
| AED location: | [Trailer / building] |
| Suspended-worker rescue plan: | ☐ Written rescue plan + drill date documented ☐ Rescue contractor on call |
| Communication chain — site → office: | [Foreman → Site Super → PM → Principal → Owner's rep] |
| Communication chain — site → GC: | [Foreman → GC Super → GC PM → GC Safety] |
| After-hours emergency contact: | [Erector PM cell + backup] |

| Wind stop-work threshold for routine lifts: | [mph sustained / gust]— typical 25/35 |
| --- | --- |
| Wind stop-work threshold for critical lifts: | [mph]— typical 20/30 |
| Lightning evacuation trigger: | [Distance miles]— typical <6 mi |
| Lightning re-start delay after last strike: | [Minutes]— typical 30 min |
| Rain / icing — decking work: | ☐ Cease decking when surface wet ☐ Per fall-protection plan |
| Cold-temperature welding (AWS D1.1 §5.12): | ☐ Preheat per WPS ☐ Stop below[°F] |
| Heat-stress protocol: | ☐ Hydration, shade, mandatory breaks per OSHA NEP |
| Weather forecast source: | [NWS / vendor — checked at start of each shift] |
| Stop-work authority: | Any worker may stop work for safety; documented on Daily Field Report. |

| Day 1 date: | [Date] |
| --- | --- |
| Day 1 site arrival time: | [HH:MM] |
| Mandatory Day 1 orientation (every worker): | ☐ GC orientation completed ☐ Site-specific erector orientation completed |
| First lift — element + location: | [e.g., Column A.1, gridline A/1] |
| First lift weight: | [lbs] |
| First lift radius: | [ft] |
| First lift crane configuration: | [Boom / Counterweight / Outriggers] |
| First lift rigging: | [Slings / shackles / spreader] |
| Toolbox topic for Day 1: | [Site orientation, fall protection 15-ft trigger, exclusion zones] |
| Day 1 goal: | [# columns set, # bolts in, plumb-up first bay] |

| # | Action Item | Owner | Due Date | Status |
| --- | --- | --- | --- | --- |
| 1 | [Description] | [Person/Firm] | [Date] | ☐ Open ☐ Closed |
| 2 | [Description] | [Person/Firm] | [Date] | ☐ Open ☐ Closed |
| 3 | [Description] | [Person/Firm] | [Date] | ☐ Open ☐ Closed |
| 4 | [Description] | [Person/Firm] | [Date] | ☐ Open ☐ Closed |
| 5 | [Description] | [Person/Firm] | [Date] | ☐ Open ☐ Closed |
| 6 | [Description] | [Person/Firm] | [Date] | ☐ Open ☐ Closed |

[Anchor-rod variances, design clarifications, scope ambiguity, etc.]

| Recurring coordination meeting cadence: | [Weekly / Biweekly] |
| --- | --- |
| Next meeting date: | [Date] |
| Next meeting agenda items: | [List] |

The undersigned acknowledge attending the Pre-Erection Meeting on the date above, receiving the documents referenced, and committing to the coordination obligations recorded in this checklist. Signatures below confirm receipt only; substantive disagreements (if any) shall be documented in Section 14 as open issues.

| Role / Firm | Printed Name | Signature | Date |
| --- | --- | --- | --- |
| Steel Erector PM | [Name] |  |  |
| Steel Erector Site Super | [Name] |  |  |
| Controlling Contractor PM | [Name] |  |  |
| Controlling Contractor Safety | [Name] |  |  |
| EOR rep (if present) | [Name] |  |  |
| Fabricator rep (if present) | [Name] |  |  |
| Crane Lift Director | [Name] |  |  |
| Concrete sub (foundations/embeds) | [Name] |  |  |
| Decking sub (if separate) | [Name] |  |  |
| Owner's rep (if present) | [Name] |  |  |

☐ Steel Erector PM (original + project file)

☐ Steel Erector Site Super (jobsite trailer)

☐ Controlling Contractor PM

☐ Controlling Contractor Safety Officer (jobsite + main office)

☐ EOR (electronic copy)

☐ Fabricator (electronic copy)

☐ Crane vendor / Lift Director

☐ Each downstream sub at the meeting

☐ Owner's rep / CM

Document version: 2026-05-17 (v1.0) — ContrPro Steel Erection trade pack. Agenda structure parallels AISC Code of Standard Practice §4.3 and 29 CFR 1926.752 without reproducing copyrighted material. Federal regulations and AISC references current as of January 2026; verify against latest CFR + AISC publications.