## Instructions
SUB SCHEDULE OF VALUES — Instructions
WHAT THIS WORKBOOK IS
This is the sub-perspective companion to AIA G-703 (Continuation Sheet for an Application for Payment). It lets you (1) schedule your Subcontract Sum across line items in SOV Setup, (2) bill monthly progress against those line items on the Pay App — Current Period tab, and (3) maintain a 12-month rolling history of billings on the Pay App — History tab.
WHY A SUB NEEDS ITS OWN SOV
Even when the GC supplies a G-702 / G-703 to be returned with each pay app, the sub should maintain its own SOV ledger because: (a) the GC version is project-specific and will be filed with the GC's pay app, not yours; (b) retainage release tracking, lower-tier sub billings, and stored-materials values often diverge between what you submit to the GC and what your accounting actually tracks; and (c) if a dispute arises over partial payment or retainage, your own internal ledger is the evidentiary record.
WORKFLOW — MONTHLY PAY APP
1. Set up SOV Setup once at Subcontract execution. Each line item has a description, a CSI division/section, and a scheduled value. The scheduled values must sum to the Subcontract Sum on Project Info.
2. At the end of each billing period (typically the 25th of the month for billing on the 1st of the next month, but confirm against the Subcontract), open Pay App — Current Period.
3. For each line item, enter the % complete this period (column F). The workbook calculates this-period dollars, total-to-date dollars, retainage held, and net amount this period.
4. Add stored materials values from the Stored Materials Log to the appropriate line items.
5. Verify the totals against the GC's G-702 summary if the GC has issued one.
6. After the GC has accepted and paid the pay app, transfer the column G (total to date) values into the next month's column on Pay App — History.
RETAINAGE HANDLING
Default retainage rate is set on Project Info (5% or 10% — confirm against Subcontract). Retainage is held on completed-work value and (depending on state law and Subcontract language) on stored materials. The workbook supports either treatment: set 'Retain on stored materials?' on Project Info to Yes or No. If your state caps retainage at a lower rate (e.g., CA at 5%), update the rate before first pay app. If your Subcontract allows retainage reduction at 50% Substantial Completion (an industry-standard provision), keep the rate at the full 10% in this workbook and reduce it on the specific pay app where reduction is requested.
STORED MATERIALS
Stored materials are billable when (a) the Subcontract permits it, (b) the materials are stored at a location protected from theft and weather, (c) materials are dedicated to the Project (segregated and labeled, with title transferring to Owner when billed), and (d) insurance / bonding is in place per the Subcontract. Use the Stored Materials Log to document each item, location, insurance, and lien waiver from the supplier.
TIPS
- Never bill more than is physically complete. Front-loading the SOV (overweighting early line items like mobilization or layout) is a flag the GC's PM will catch and creates compounding problems on Subcontract close-out.
- Track every change order in a separate row on SOV Setup with a 'CO #' prefix; do not modify the scheduled value of base-bid line items.
- The 'Variance' column on SOV Setup compares the billed-to-date amount to the scheduled value. A consistently negative variance late in the project is the early warning of either scope creep that should have been a change order or front-loading that is now catching up.
- At Substantial Completion, the retainage held in column J should match the GC's accounting; reconcile before requesting retainage release.
ON CSI MASTERFORMAT
Each SOV line carries a CSI division and section. CSI MasterFormat is the industry standard for categorizing construction work — coding the SOV this way lets the GC's accounting system map your bills to its own job-cost ledger and lets you roll up totals by trade across projects.
TROUBLESHOOTING
- 'Variance' column shows red: billed exceeds scheduled. Either bill less this period or add a change order on SOV Setup for the overage.
- SOV Setup totals don't equal Subcontract Sum on Project Info: cross-check each line, and confirm no rows are blank or missing values. The cell C5 of Project Info validates this.
- Retainage on Pay App doesn't match GC's: confirm Project Info retainage rate matches Subcontract and confirm 'Retain on stored materials?' setting matches the GC's practice.

## Project Info
PROJECT INFORMATION
Project Name
Project No. (GC's)
Subcontract No.
Subcontractor (legal name)
General Contractor (legal name)
Owner
Project Address
Trade / Scope
CSI Division (primary)
Subcontract Date
Original Subcontract Sum | 0
Approved Change Orders to date | 0
Current Subcontract Sum (Orig + COs)
Retainage Rate (%) — confirm Subcontract | 10%
Retain on stored materials? | No
Pay App Submission Deadline (day of month) | 25
Pay App Payment Due (days after GC acceptance) | 30
Project Manager (Sub)
Project Manager (GC)
SOV TOTAL VALIDATION
SOV Setup line-item total:
Current Subcontract Sum:
Variance (should be $0):

## SOV Setup
SOV SETUP — Line Items
Set up one row per Subcontract line item. Scheduled Value must sum to Current Subcontract Sum on Project Info. Add change orders as separate rows prefixed 'CO #'.
Line # | Description | CSI Div | CSI Section | Scheduled Value ($) | % of Subcontract | Billed To Date ($) | Balance to Finish ($) | Variance | Type | Notes
TOTAL

## Pay App - Current
PAY APPLICATION — Current Period
Project: =ProjectName | [5 empty] | Period: |  | Pay App #: | 1
Line # | Description | CSI Div | Scheduled Value | Work Completed Previous ($) | % Complete This Period | Work Completed To Date ($) | Materials Stored ($) | Total To Date ($) | % Complete | Retainage ($) | Balance to Finish ($) | This Period Net ($)
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
|  |  |  | 0 | 0% |  | 0
GRAND TOTAL
PAY APP SUMMARY
Total Subcontract Sum (incl. approved COs)
Total Completed & Stored to Date
Total Retainage Held
Total Earned Less Retainage
Less Previous Certificates for Payment
CURRENT PAYMENT DUE
Balance to Finish (Including Retainage)

## Pay App - History
PAY APP HISTORY — 12-Month Roll-Up
After each pay app is paid by the GC, transfer the Total To Date values from Pay App — Current Period into the next column below.
Line # | Description | Scheduled Value | Period 1 | Period 2 | Period 3 | Period 4 | Period 5 | Period 6 | Period 7 | Period 8 | Period 9 | Period 10 | Period 11 | Period 12 | Final To Date
TOTAL

## Stored Materials
STORED MATERIALS LOG
Track materials billed-but-not-installed. The GC's pay-app reviewer will require evidence of off-site or on-site storage, dedicated segregation/labeling, insurance coverage, and a supplier lien waiver before approving stored-materials value.
Date Added | SOV Line Ref | Description | Supplier | PO # | Quantity | Unit | Unit Cost | Total Value ($) | Storage Location | Insured? | Lien Waiver from Supplier? | Date Installed | Status
TOTAL

## CSI Reference (hidden)
CSI MasterFormat Divisions
Div | Name
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities
34 | Transportation
35 | Waterway and Marine Construction
40 | Process Interconnections
41 | Material Processing and Handling Equipment
42 | Process Heating, Cooling, and Drying Equipment
43 | Process Gas and Liquid Handling, Purification, and Storage Equipment
44 | Pollution and Waste Control Equipment
45 | Industry-Specific Manufacturing Equipment
46 | Water and Wastewater Equipment
48 | Electrical Power Generation
49 | Reserved