Sections 1-4 are a guide explaining why a Daily Field Report (DFR) matters, what it captures, and how it functions as evidence in disputes. Sections 5-6 contain the printable DFR form (paper backup for the field) and the closeout/weekly summary form. The companion workbook Daily_Field_Report.xlsx contains a digital version with one tab per day for a full month plus an auto-rolling summary tab. Use the paper form in the field if the digital workflow is impractical; transcribe to the workbook the same day.

Section 1 — Why the DFR Exists

Section 2 — What a DFR Captures

Section 3 — Field Discipline

Section 4 — How DFRs Are Used (Disputes, Audits, Closeout)

Section 5 — Daily Field Report Form (Printable)

Section 6 — Weekly Roll-Up Summary (Printable)

Section 7 — Foreman's Pre-Sign Checklist

A DFR serves four overlapping purposes:

Project-management record. A real-time record of crew, productivity, weather, schedule, and conditions, used by the PM to manage the project, forecast remaining work, and identify problems early.

Evidence preservation. The first record of an event on the project, written contemporaneously and signed by a participant — the strongest form of evidence in a construction dispute. Memory of an event a year later is impeachable; a contemporaneous DFR is not.

Schedule and productivity reporting. A consolidated daily record that supports the sub's monthly productivity reports, manpower forecasts, and schedule recovery plans.

Compliance documentation. Required by many Subcontracts. On prevailing-wage and federal projects, DFRs support certified-payroll classifications. On safety-sensitive projects, DFRs document toolbox talks, safety meetings, and incidents.

| Category | What to record |
| --- | --- |
| Identifying info | Date; day-of-week; DFR number (sequential); project; sub; foreman name |
| Weather | AM/PM temp; precipitation; wind; impact on work (none / minor / lost time) |
| Crew | Each worker name; classification; ST/OT hours; tasks (with location/elevation) |
| Subcontractor / lower-tier | Lower-tier subs on site; their crew counts and scope |
| Equipment on site | Each piece; owned or rented; operating hours; idle hours |
| Materials delivered or installed | What arrived; what was installed; quantities; supplier |
| Work performed | Narrative — what crews accomplished; reference drawings/specs/RFIs |
| Schedule notes | Activities started / completed; status vs. baseline; lookahead drift |
| Conditions affecting work | Differing site conditions; missing GC trades; access issues; utilities; inspections |
| Directives / changes | Any GC directive issued today; T&M tickets opened; RFIs issued or answered |
| Visitors | Owner, architect, engineer, inspector, AHJ, third-party visit; sign-in if required |
| Safety | Toolbox topic; near-miss; first aid; incident; PPE compliance audit; OSHA visit |
| Quality | Inspections passed/failed; testing performed; non-conforming materials |
| Photos | Photo log: file name / description / time / location; attached separately |
| Open issues | Issues escalated to the office; follow-up needed |
| Foreman signature + GC field-rep signature (optional) | Signed at end of shift; same-day countersignature is gold |

A DFR system is only useful if foremen actually fill it out. The four habits the sub's PM enforces:

Same-day rule. DFRs are completed and signed before the foreman leaves the site for the day. "I'll do it tomorrow morning" is the start of a DFR file with holes.

Specific, not generic. "Worked on south wall framing" is not a DFR entry. "Framed exterior wall sections E-1 through E-4 at south elevation; installed 18 ga metal studs, 16" o.c., 14'-6" tall; awaiting MEP rough-in for ECS-3 routing before sheathing" is. The specific entry is what survives in a dispute; the generic entry is what loses.

Photographs every day. A minimum of 6-8 photos per day, geo-tagged and time-stamped, covering the locations the crew worked. Phone cameras are universally available; the marginal cost is zero; the marginal value in disputes is enormous.

Flag conditions immediately. If a condition affecting work appeared today (a missing trade, an unexpected access restriction, a wet basement, an electrical de-energization), the DFR identifies it AND the foreman raises it the same day with the GC field rep. Quiet documentation that does not result in a directive is later impeached as "you didn't think it was important enough to raise" — defeating the contemporaneous-evidence argument.

| Use case | DFR entries that matter |
| --- | --- |
| Defending a backcharge for "your crew damaged X" | Crew location entries (showing crew was not at X); photos of X before and after; visitor log (third parties on site at X) |
| Pricing a change order for added work | Crew hours allocated to the change directive; equipment used; materials consumed; productivity vs. base scope |
| Asserting a delay claim for late GC trade | Lookahead activities prevented by the missing trade; idle crew hours; rescheduling impact |
| Defending a defect claim post-completion | Inspections passed on the day of installation; installer's signature; materials traceability |
| Documenting a constructive change (no Change Order issued) | The directive in the DFR; the foreman's notation that "this exceeds the bid scope per RFI #__"; the field rep's countersignature; preserving claim per Subcontract notice provisions |
| OSHA investigation | Toolbox topics that day; PPE inspection notes; near-miss entries |
| Closeout punch list dispute | Inspection records and photos of completed work on date of substantial completion; what was complete vs. punch-list |

One page per day. Print or save as PDF and store with the project file. The XLSX companion has the same fields in digital form.

| DFR #: | [Sequential #] | Date: | [Date] |
| --- | --- | --- | --- |
| Day: | [Sun/Mon/...] | Workweek #: | [#] |
| Project: | [Project Name] |  |  |
| Sub: | [Subcontractor Legal Name] |  |  |
| Foreman: | [Name] | Sub's PM: | [Name] |

| AM Temp / Conditions: | [°F / Clear / Rain / Snow] |
| --- | --- |
| PM Temp / Conditions: | [°F / Clear / Rain / Snow] |
| Wind / Visibility: | [mph / Notes] |
| Impact on Work: | ☐ None ☐ Minor ☐ Hours lost (specify):[Description] |

| Name | Classification | ST Hrs | OT Hrs | Task / Location |
| --- | --- | --- | --- | --- |
| [Name] | [Class] | [#] | [#] | [Task] |
| [Name] | [Class] | [#] | [#] | [Task] |
| [Name] | [Class] | [#] | [#] | [Task] |
| [Name] | [Class] | [#] | [#] | [Task] |
| [Name] | [Class] | [#] | [#] | [Task] |
| [Name] | [Class] | [#] | [#] | [Task] |
| Crew Totals | [Σ] | [Σ] |  |  |

| Firm | Trade | Crew | Scope Today |
| --- | --- | --- | --- |
| [Firm] | [Trade] | [#] | [Notes] |
| [Firm] | [Trade] | [#] | [Notes] |

| Equipment | Owned / Rented | Hrs Operating | Hrs Idle | Notes |
| --- | --- | --- | --- | --- |
| [Equipment] | [Type] | [#] | [#] | [Notes] |
| [Equipment] | [Type] | [#] | [#] | [Notes] |

| Material | Supplier | Qty Delivered | Qty Installed | Location |
| --- | --- | --- | --- | --- |
| [Material] | [Supplier] | [Qty] | [Qty] | [Location] |
| [Material] | [Supplier] | [Qty] | [Qty] | [Location] |

[Specific narrative — locations, drawings/specs referenced, progress, productivity notes]

| Differing site conditions: | ☐ None ☐ Yes:[Describe] |
| --- | --- |
| Missing GC trade / access: | ☐ None ☐ Yes:[Describe] |
| Utility / power: | ☐ None ☐ Issue:[Describe] |
| Inspection / AHJ: | ☐ None ☐ Yes:[Inspector / outcome] |
| Idle crew hours due to conditions: | [# / Reason] |

| # | Type | Originator | Description | Status |
| --- | --- | --- | --- | --- |
| 1 | [Directive / RFI / T&M / Submittal] | [GC PM / Field Eng] | [Description] | [Status] |
| 2 | [Type] | [Originator] | [Description] | [Status] |

[Owner / Architect / Engineer / Inspector / AHJ — name, time, purpose]

| Toolbox topic: | [Topic] |
| --- | --- |
| Near-miss / first aid / incident: | ☐ None ☐ Reported (separate Incident Report) |
| PPE audit notes: | [Notes] |
| OSHA visit: | ☐ None ☐ Yes:[Inspector / outcome] |

| File / Frame | Time | Location | Description |
| --- | --- | --- | --- |
| [File] | [hh:mm] | [Location] | [Description] |
| [File] | [hh:mm] | [Location] | [Description] |
| [File] | [hh:mm] | [Location] | [Description] |
| [File] | [hh:mm] | [Location] | [Description] |

[List items for PM follow-up]

| Foreman: | [Signature / Print / Date] |
| --- | --- |
| GC Field Rep (countersignature — optional but valuable): | [Signature / Print / Date] |

Completed by Sub's PM at the end of each workweek. Submitted to GC with the weekly progress report.

| Project: | [Project Name] |
| --- | --- |
| Sub: | [Subcontractor Legal Name] |
| Week Ending: | [Saturday] |
| DFRs Included: | [DFR # — DFR #] |

| Day | Date | Crew Size | ST Hrs | OT Hrs | Total |
| --- | --- | --- | --- | --- | --- |
| Sun | [Date] | [#] | [#] | [#] | [#] |
| Mon | [Date] | [#] | [#] | [#] | [#] |
| Tue | [Date] | [#] | [#] | [#] | [#] |
| Wed | [Date] | [#] | [#] | [#] | [#] |
| Thu | [Date] | [#] | [#] | [#] | [#] |
| Fri | [Date] | [#] | [#] | [#] | [#] |
| Sat | [Date] | [#] | [#] | [#] | [#] |
| Totals | [Σ] | [Σ] | [Σ] |  |  |

[Reference Schedule activity IDs and locations]

[List]

[Activities planned]

[Items]

| Recordable incidents this week: | [#] |
| --- | --- |
| Near misses: | [#] |
| First aid only: | [#] |
| OSHA visits: | [#] |
| Toolbox topics covered: | [List] |

☐ Date and DFR number entered.

☐ Crew names, classifications, hours, and tasks all populated — no "see other" or "TBD".

☐ Crew hour totals add up to the daily timecard total.

☐ Weather entered, with impact on work flagged if any.

☐ Equipment list complete.

☐ Materials delivered logged (with delivery ticket attached or referenced).

☐ Work-performed narrative is specific — references drawings, specs, locations.

☐ Conditions affecting work flagged where applicable.

☐ Any directive / RFI / T&M issued today is captured.

☐ At least six photos taken; photo log entries populated.

☐ Open issues escalated to office in writing.

☐ Foreman signature applied.

☐ GC field rep countersignature requested (collect when possible — same-day is gold).

☐ Filed in project DFR folder (paper) and uploaded to project drive (digital) the same day.

Document version: 2026-05-17 (v1.0) — ContrPro Universal Sub Suite. The Daily Field Report form structure mirrors common commercial industry practice. Use the companion Daily_Field_Report.xlsx for the digital workflow; retain paper or scanned DFRs for 3-7 years per the controlling Subcontract and applicable statute-of-repose.