## Instructions
ContrPro - Accounts Payable (AP) Tracker
Mirror image of the AR Tracker - what YOU owe vendors, subs, and suppliers. Cash flow and lien-waiver discipline live here.
What this workbook is
Five visible tabs plus a hidden CSI Reference. Company Info anchors your entity, Vendor Invoice Log is the main worksheet, Aging Summary buckets exposure by vendor type, and Dashboard surfaces the two metrics that wreck contractors: Subs Paid Without Lien Waiver and Subs On Site With Expired COIs.
Every bill you receive goes in the Vendor Invoice Log. The aging math is automatic - you fill in dates and amounts, the workbook tells you what's due this week, what's late, and which payments carry risk.
Vendor vs sub vs material supplier - tag every row
Subcontractor - performs labor on site. Owes you a lien waiver before AND after payment. Must carry current COI naming you as additional insured. Highest risk per dollar - mechanic's-lien exposure.
Material Supplier - delivers materials, no on-site labor. May still have lien rights (depends on state). Joint check agreements common when supplier sells through your sub.
Equipment Rental - cranes, lifts, generators. Time-and-materials billing. Watch for damage waivers and fuel/run-time true-ups.
Service - utilities, dumpsters, sanitation, professional services (engineer, surveyor, attorney).
Other - catch-all. Use sparingly; re-tag when you can.
Lien waiver workflow - DO NOT pay without one
Conditional waiver - get from sub BEFORE you cut the check. Says 'lien rights waived CONDITIONAL on receipt of payment.' Protects you the moment the funds clear. Required at every progress payment.
Unconditional Partial - get AFTER the check clears, for the amount actually paid. Says 'lien rights waived up to $X paid through date Y.' Required to close out each pay cycle.
Unconditional Final - get on the FINAL payment after the check clears. Says 'all lien rights waived, paid in full.' Required to close the job.
If the Status is Paid and Lien Waiver Received is None - that row turns red. Track it down NOW. Every day you let it sit, the sub has a longer window to lien your project.
Trust fund implications - this is statutory law in some states
Texas Construction Trust Fund Act (Tex. Prop. Code Ch. 162): money you receive from an owner is held in TRUST for downstream subs and suppliers. Spending it on overhead before paying subs is a felony in Texas. Pay your subs from project money first - period.
New York Lien Law Article 3-A: similar statutory trust. Funds received are trust funds; diversion is larceny. Personal liability for officers/managers who divert.
Maryland, Michigan, Minnesota, New Jersey, Washington, Wisconsin, Illinois (residential): comparable trust fund or prompt-payment statutes. Confirm your state with counsel before assuming you're free to commingle project receipts with operating cash.
The Total Retainage Held figure on the Dashboard is the dollar amount you have BACK-pocketed from subs. In trust-fund states, that money may be statutorily owed - get the lien waiver, release on the contract milestone, do not sit on it past the agreed release date.
COI (Certificate of Insurance) discipline
Every sub on site MUST have current general liability + workers comp coverage naming you as additional insured. Expired = stop work, no exceptions.
COI Current column: Yes / No / Expired / N/A. If Expired or No appears on a sub with an open balance, that row turns red and the Dashboard increments the COI risk counter.
Material suppliers and most services are N/A. Equipment rentals usually require a different certificate type (rental liability). Use your judgment - the dropdown is a tool, not a doctrine.
Aging buckets and prompt-payment statutes
Current - not yet past due. Pay on the negotiated terms.
1-30 - 1 to 30 days past due. Sub will start calling. Most states' prompt-payment statutes trigger interest in this window (commonly 1-2% per month).
31-60 - 31 to 60 days. Sub may stop work. State licensing boards take complaints seriously.
61-90 - 61 to 90 days. Most state prompt-pay statutes have ALREADY granted statutory interest. Sub may file a stop-work notice or mechanic's lien.
91-120 - 91 to 120 days. Lien is likely. Bond claim if you bonded the job.
120+ - over 120 days. Litigation or bond claim is probably already in motion.
Note: many states' prompt-payment statutes require GC to pay subs within 7-30 days of receiving owner payment for that sub's work. Falling outside that window can void contract defenses.
Color coding cheat sheet
Aging Bucket: green = Current/Paid, yellow = 1-30/31-60, orange = 61-90, red = 91-120/120+.
Lien Waiver: RED if Status is Paid and Waiver is None - you paid a sub without protection.
COI Current: RED if No or Expired - sub is on site without coverage.
Status: green = Paid, yellow = Received/Approved for Payment, red = On Hold/Disputed.
Tab-by-tab quick start
1. Company Info - your entity name, EIN, primary state, and any AP-specific notes.
2. Vendor Invoice Log - one row per bill. Pick Vendor Type and CSI Division from dropdowns. Fill in Amount, Retainage Withheld, Date Due, Date Paid, Amount Paid. Outstanding, Aging, and Days Outstanding all calculate. Set Lien Waiver and COI status honestly - the risk panel depends on it.
3. Aging Summary by Vendor Type - DO NOT edit. Cross-tabs aging x vendor type.
4. Dashboard - DO NOT edit. Top of stack: outstanding AP, retainage held from subs, subs with bad COIs, subs paid without waivers, DPO, aging panel.
Weekly cadence
Monday morning: open Dashboard. Anything red gets handled before lunch. COI-expired subs - call them off site until they email a current cert.
Wednesday: pay run. Cut checks ONLY against rows with a current conditional waiver on file. If you have to pay without one, document why in Notes and chase the unconditional inside 5 business days.
Friday afternoon: log every bill received and payment made this week. Reconcile against the bank.
End of month: tie Total Outstanding AP to your accounting system. They must match. Reconcile retainage held to your sub contracts.
Tabs in this workbook
Instructions - this tab
Company Info - your entity anchor
Vendor Invoice Log - CSI-coded bill line items, the main worksheet
Aging Summary by Type - aging x vendor type cross-tab
Dashboard - AP headline, risk flags, DPO, aging panel
CSI Reference - canonical division list (hidden - do not edit)
ContrPro - built for builders. Questions: support@contrpro.com

## Company Info
Company Information
Company Name | EIN | Primary State | Notes
EXAMPLE - Acme Construction LLC | 12-3456789 | TX | Texas Construction Trust Fund Act applies - pay subs from project receipts first.

## Vendor Invoice Log
Vendor Invoice Log (CSI MasterFormat)
Invoice / Bill Number | Date Received | Vendor / Supplier / Sub | Vendor Type | CSI Division | CSI Code | Division Name | Project / Job | Description | Amount | Retainage Withheld | Net Payable | Date Due | Date Paid | Amount Paid | Outstanding | Days Outstanding | Aging Bucket | Lien Waiver Received? | COI Current? | Status | Notes
B-2001 | 2026-03-15 | Pacific Steel Erectors | Subcontractor | 05 | 05 12 00 |  | Riverside Office Bldg | Pay App #2 - Structural steel erection, Level 1-2. | 58400 | 2920 |  | 2026-04-14 | 2026-04-12 | 55480 |  |  |  | Unconditional Partial | Yes | Paid | Paid via ACH. Conditional issued with invoice, unconditional received after funds cleared. COI on file thru 2026-09-30.
B-2002 | 2026-04-30 | Apex Plumbing & Mechanical | Subcontractor | 22 | 22 10 00 |  | Riverside Office Bldg | Pay App #3 - Plumbing rough-in, Level 2. | 34200 | 1710 |  | 2026-05-30 |  | 0 |  |  |  | Conditional | Yes | Approved for Payment | Pay app reviewed and approved. Conditional waiver on file. Releasing check this week on receipt of unconditional partial.
B-2003 | 2026-03-02 | Heartland Lumber Supply | Material Supplier | 06 | 06 10 00 |  | Riverside Office Bldg | Framing lumber package - Level 2 partitions. | 11850 | 0 |  | 2026-04-01 |  | 0 |  |  |  | N/A | N/A | Received | Material supplier - no retainage, no COI required (off-site delivery). Disputing 12 sticks short on tally. Hold check pending credit memo.
B-2004 | 2026-02-12 | Bayside Electric LLC | Subcontractor | 26 | 26 50 00 |  | Pinnacle Tower Renovation | Pay App #1 - Lighting rough-in & fixture install Level 3. | 22600 | 1130 |  | 2026-03-14 |  | 10000 |  |  |  | Conditional | Expired | On Hold | RISK: Sub COI expired 2026-04-30. Required new cert before next payment. Partial payment was released before expiry. Follow-up sent 2026-05-05; no response. Stop further on-site work.
B-2005 | 2026-01-22 | Granite Concrete Cutters | Subcontractor | 03 | 03 30 00 |  | Pinnacle Tower Renovation | Saw-cut & remove existing SOG for new MEP chase. | 8650 | 0 |  | 2026-02-21 | 2026-02-19 | 8650 |  |  |  | None | Yes | Paid | RISK: Paid in full without any lien waiver received. Followed up twice for unconditional final - radio silence. Lien exposure window still open per state statute. Escalate to attorney if not resolved by 5/20.
TOTALS
Formulas:
Days Outstanding = IF(OR([Date Due]="",IFERROR([Outstanding],0)<=0),"",MAX(0,TODAY()-[Date Due]))
Aging Bucket = IF(AND([Date Paid]<>"",IFERROR([Amount Paid],0)>=IFERROR([Net Payable],0),IFERROR([Net Payable],0)>0),"Paid",IF([Date Due]="","",IF(TODAY()-[Date Due]<=0,"Current",IF(TODAY()-[Date Due]<=30,"1-30",IF(TODAY()-[Date Due]<=60,"31-60",IF(TODAY()-[Date Due]<=90,"61-90",IF(TODAY()-[Date Due]<=120,"91-120","120+")))))))

## Aging Summary by Type
AP Aging Summary by Vendor Type
Reads from Vendor Invoice Log via COUNTIFS / SUMIFS - do not edit. Cross-tabs aging bucket by vendor type. Material Supplier + Equipment Rental + Service + Other are rolled into the 'Other' columns.
Aging Bucket | Subcontractor Count | Sub $ | Supplier Count | Supplier $ | Other Count | Other $
Current
1-30
31-60
61-90
91-120
120+
TOTAL OUTSTANDING

## Dashboard
Accounts Payable Dashboard
Auto-calculated from Company Info and Vendor Invoice Log. Update those tabs - this one stays in sync. Pay extra attention to the two RISK rows: paying subs without lien waivers and subs on site with expired COIs.
AP Headline
Total Outstanding AP
Total Retainage Held (from subs)
Total Paid YTD
Avg Days to Pay (DPO equivalent)
Risk Flags - These Are Where CFOs Lose Sleep
Subs without current COI (open exposure)
Subs paid without lien waiver - count
Subs paid without lien waiver - $ exposure
Aging Breakdown
Aging Bucket | Count | Outstanding
Current
1-30
31-60
61-90
91-120
120+
TOTAL OUTSTANDING

## CSI Reference (hidden)
CSI MasterFormat Division Reference
Pulled from the same canonical list as ContrPro Job Costing. Do not edit.
CSI Division | Division Name
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities
34 | Transportation
35 | Waterway and Marine Construction
40 | Process Interconnections
41 | Material Processing and Handling Equipment
42 | Process Heating, Cooling, and Drying Equipment
43 | Process Gas and Liquid Handling, Purification, and Storage Equipment
44 | Pollution and Waste Control Equipment
45 | Industry-Specific Manufacturing Equipment
46 | Water and Wastewater Equipment
48 | Electrical Power Generation
49 | Reserved