## Instructions
ContrPro - Change Order Log
CSI MasterFormat-coded log of every change to a construction contract - the receipt drawer for the job.
What this workbook is
Six tabs work together: Project Info pins the contract, Change Order Log is where every CO lives, CO Summary by Division rolls them up by trade, and Dashboard shows contract impact at a glance. CSI Reference is a hidden-ish lookup list - leave it alone.
Every row in Change Order Log is one paper trail: written description, dollar amount, schedule impact, and approval status. If it is not in this log, it did not happen.
Change Order vs Scope Creep vs RFI - know the difference
Change Order (CO) - A WRITTEN amendment to the contract that adjusts price, schedule, or scope. It is bilateral (owner and GC both sign) and binding. This log only tracks COs.
Scope Creep - Owner or architect asks for 'just one more thing' verbally and you do it. DO NOT track scope creep here, track it as a CO the moment you sense it. Verbal is not a CO; verbal is unpaid work waiting to happen.
RFI (Request for Information) - A question to the design team. Not a CO. But the answer often TRIGGERS a CO when the response changes scope or quantities. Log the resulting CO here and reference the RFI number in Notes.
When to issue a formal CO vs a T&M ticket
Formal CO (Lump Sum / Unit Price / Allowance / Deductive) - Use when scope is defined enough to price up-front. Get it signed BEFORE the work starts. This is the cleanest path and protects your margin.
T&M (Time and Material) ticket - Use when scope is unclear or urgent (emergency repair, hidden condition). Track labor hours and material receipts daily, get signed T&M tickets each day, and roll them into a CO weekly. Type = T&M on the row.
Rule of thumb: if you cannot say what the work is in one sentence, it is T&M until you can.
The CO Log and retainage discussions
Retainage (typically 5-10% withheld from pay apps) gets released at substantial completion. Owners will scrutinize every CO before cutting that final retainage check.
A clean CO Log - with descriptions, reasons, signed approvals, and CSI coding - is what gets retainage released on time. A messy log is what funds 90-day retainage disputes.
Before requesting retainage release, sort this tab by Status, confirm every Approved row has an approver name and date, and resolve every Pending/Disputed row.
Statute of Limitations awareness
Most U.S. states impose a 4-year statute of limitations on construction defect claims for breach of contract (some go to 6 or 10 - check your state). Some states also have a statute of repose (often 10-12 years) that caps liability regardless of when a defect is discovered.
What this means for the log: keep this file for AT LEAST the full statute of repose window after substantial completion. Cloud backup it. PDF the final version with all approvals and store it with the contract.
This workbook is a record-keeping tool, not legal advice. Run anything that smells like a dispute past your construction attorney.
Tab-by-tab quick start
1. Project Info - fill in Project Name, Number, Client, Original Contract Amount, PM, and Architect/Engineer on row 4. The Dashboard reads Original Contract Amount from D4.
2. Change Order Log - one row per CO. Fill in CO Number, dates, project, CSI Division (dropdown), CSI Code (6-digit text, e.g. 23 30 00), Division Name (auto-filled from VLOOKUP), description, reason, type, amount, schedule impact, status, approver.
3. CO Summary by Division - DO NOT edit. It rolls up your CO Log automatically.
4. Dashboard - DO NOT edit. Read-only summary of contract impact and CO counts by status.
CSI coding rules (must follow)
CSI Division: 2-digit text (01-49). Pick from the dropdown - this preserves leading zeros and matches the canonical list.
CSI Code: 6-digit space-separated, e.g. 23 30 00 for HVAC Air Distribution. You can extend to Level 3 (e.g. 23 31 13) for finer detail.
Division Name auto-fills from a VLOOKUP against CSI Reference. If it shows #N/A, your CSI Division value does not match the reference list - re-pick from the dropdown.
Color coding cheat sheet
Amount column: green = positive (you're getting paid more), red = negative (deductive CO).
Status column: green = Approved, yellow = Pending or Submitted, red = Rejected or Disputed.
Dashboard CO % of Contract: highlighted red when total approved COs exceed 15% of original contract - that's the threshold where most owners start asking hard questions and lenders may trigger a review.
Weekly cadence
Monday: review Pending and Submitted rows. Anything older than 14 days gets a follow-up email today.
Friday: log every CO issued this week. No CO leaves the trailer unrecorded.
End of month: reconcile CO totals against pay app G-703 line items. They must match - this is what your owner's accountant will check.
Tabs in this workbook
Instructions - this tab
Project Info - contract anchor (Dashboard reads Original Contract Amount from here)
Change Order Log - CSI-coded line items, the main worksheet
CO Summary by Division - SUMIFS roll-up by division and status
Dashboard - contract impact, CO counts, schedule impact
CSI Reference - canonical division list (do not edit)
ContrPro - built for builders. Questions: support@contrpro.com

## Project Info
Project Information
Project Name | Project Number | Client | Original Contract Amount | Project Manager | Architect / Engineer | Notes
EXAMPLE - Riverside Office Bldg | 2026-014 | Riverside Holdings LLC | 1850000 | Sample PM | Apex Architects + WSP Structural | Example row - replace with your project.

## Change Order Log
Change Order Log (CSI MasterFormat)
CO Number | Date Issued | Date Approved | Project / Job | CSI Division | CSI Code | Division Name | Description of Change | Reason | Type | Amount | Schedule Impact (days) | Status | Approved By | Notes
CO-001 | 2026-03-12 | 2026-03-18 | Riverside Office Bldg | 03 | 03 30 00 |  | Add 12 CY structural concrete at column footings F-4 to F-7 per RFI-024. | Field Condition | Lump Sum | 8450 | 2 | Approved | K. Holmes (Owner Rep) | Soft soil discovered at depth; required oversized footings.
CO-002 | 2026-03-20 | 2026-03-25 | Riverside Office Bldg | 23 | 23 30 00 |  | Upgrade VAV boxes Level 2 from std to digital controls. | Owner Request | Lump Sum | 14275 | 0 | Approved | K. Holmes (Owner Rep) | Owner spec upgrade after value-engineering pass.
CO-003 | 2026-04-02 |  | Riverside Office Bldg | 09 | 09 60 00 |  | Substitute LVT flooring for spec'd carpet tile in open office. | Owner Request | Deductive | -6320 | 0 | Pending |  | Awaiting owner sign-off on LVT sample.
CO-004 | 2026-04-10 | 2026-04-15 | Riverside Office Bldg | 26 | 26 50 00 |  | Add emergency lighting at stair towers per code review. | Code Change | T&M | 3940 | 1 | Approved | K. Holmes (Owner Rep) | Updated IBC interpretation from building dept.
CO-005 | 2026-04-22 |  | Riverside Office Bldg | 07 | 07 50 00 |  | Replace damaged membrane after wind event (40 sq). | Force Majeure | Unit Price | 11200 | 5 | Submitted |  | Wind event 2026-04-19; insurance claim filed in parallel.
TOTALS

## CO Summary by Division
CO Summary by Division (auto roll-up)
Reads from Change Order Log via SUMIFS - do not edit this tab directly. One row per CSI Division.
CSI Division | Division Name | CO Count | Approved Amount | Pending Amount | Rejected Amount | Net Approved Amount | Schedule Impact (Approved)
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities
34 | Transportation
35 | Waterway and Marine Construction
40 | Process Interconnections
41 | Material Processing and Handling Equipment
42 | Process Heating, Cooling, and Drying Equipment
43 | Process Gas and Liquid Handling, Purification, and Storage Equipment
44 | Pollution and Waste Control Equipment
45 | Industry-Specific Manufacturing Equipment
46 | Water and Wastewater Equipment
48 | Electrical Power Generation
49 | Reserved
TOTALS

## Dashboard
Change Order Dashboard
Auto-calculated from Project Info and Change Order Log. Update those tabs - this one stays in sync.
Contract Impact
Original Contract Amount
Total Approved CO Amount
Total Pending CO Amount
Total Rejected CO Amount
Adjusted Contract Amount (Original + Approved)
Approved CO % of Original Contract
Total Schedule Impact - Approved (days)
CO Counts by Status
Status | Count | Amount | % of Total CO $
Approved
Pending
Submitted
Rejected
Disputed
Voided
ALL COs (any status)

## CSI Reference (hidden)
CSI MasterFormat Division Reference
Pulled from the same canonical list as ContrPro Job Costing. Do not edit.
CSI Division | Division Name
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities
34 | Transportation
35 | Waterway and Marine Construction
40 | Process Interconnections
41 | Material Processing and Handling Equipment
42 | Process Heating, Cooling, and Drying Equipment
43 | Process Gas and Liquid Handling, Purification, and Storage Equipment
44 | Pollution and Waste Control Equipment
45 | Industry-Specific Manufacturing Equipment
46 | Water and Wastewater Equipment
48 | Electrical Power Generation
49 | Reserved