## Instructions
ContrPro - Project Tracker (Portfolio View)
Portfolio-level tracker for every open job at once. The view a GC owner needs Monday morning.
What this workbook is (and what it is NOT)
This is a PORTFOLIO tracker - one row per project, all your active jobs in one view. Use Job_Costing_Spreadsheet.xlsx (per-job, CSI-coded) for the deep cost detail on any single job. Use Change_Order_Log.xlsx for the CO paper trail. This file is the bird's-eye view.
Six tabs work together: Company Info pins your company metadata, Project Portfolio holds the rows, Portfolio Summary by Status auto-rolls, and Dashboard surfaces the KPIs that matter. CSI Reference is hidden - it feeds the dropdowns.
KPIs explained (read this once - it changes how you use this file)
Backlog = Adjusted Contract minus Earned Value. The work you have under contract but haven't billed yet. This is what banks and bonding companies care about most. Healthy backlog = 6-12 months of revenue at your current burn rate.
Burn Rate = Cost to Date divided by elapsed days. Tells you how fast a job is consuming cash. Compare against EAC / total duration to spot jobs that are eating themselves.
Projected Margin % = (Adjusted Contract - Estimated Cost at Completion) / Adjusted Contract. Green > 10%, yellow 0-10%, RED < 0. A red row means you are losing money on that job - call your PM today.
% Complete = self-reported field assessment, dollar-weighted on the Dashboard. Use the field PM's number, not a calculated one - the gap between field % and earned % is a leading indicator of trouble.
Earned Value = Adjusted Contract * %Complete. This is what you SHOULD have billed by now if your schedule of values is honest.
How to use the Project Portfolio tab
One row per project. Pre-populated rows show diverse statuses (Active, Mobilizing, Substantial Completion, Awarded, Bidding) - replace them or add new rows below.
Dropdowns: Project Type, Primary CSI Division, State, Status. Pick from the list - typos break the Summary roll-up.
FORMULA columns (do NOT type into these - they calculate themselves): Adjusted Contract, Projected Gross Margin, Projected Margin %, Earned Value, Backlog.
Status colors: green for Active / Substantial Completion / Final, yellow for Mobilizing / Bidding, blue for Awarded, red for Lost. Closed shows as default.
% Complete column has a green data bar so you can scan progress visually down the column.
Company Info tab
One row with your company's metadata - Company Name, EIN, primary state of operation, and your insurance / bond carriers. The Dashboard does not pull from this tab, but downstream files (COI Tracker, Subcontractor Tracker) will reference the same fields - keep it current so a future ContrPro release can auto-fill those workbooks.
Portfolio Summary by Status (auto roll-up)
Reads Project Portfolio via COUNTIF/SUMIFS. Do not type into this tab.
Shows count, total contract, total earned, total cost-to-date, total backlog, and average margin % for every status bucket. If your active backlog drops while your closed-job count climbs, you have a sales pipeline problem - not a delivery problem.
Dashboard
Top panel = portfolio KPIs: Total Active Backlog, Total Cost to Date, Weighted Average Margin %, and Active Project Count.
Top 5 Largest Backlogs panel uses LARGE() so it always shows your biggest exposures, regardless of row order in the Portfolio tab.
Aged Projects panel flags any project where Target Completion is BEFORE today AND status is not yet Final / Closed. These are the jobs that need a hard conversation this week.
Weekly cadence (Monday review meeting)
Monday AM: open this file. Scan Dashboard KPIs first. Then scroll the Portfolio tab from top to bottom - any red margin gets a phone call before lunch.
Friday PM: PMs update % Complete, Cost to Date, and Estimated Cost at Completion on their rows. No row goes a week without an update; a stale row is a lying row.
End of month: archive a copy with a date stamp (Project_Tracker_2026-05-31.xlsx) for board reviews and lender packages.
Tabs in this workbook
Instructions - this tab
Company Info - one-row company metadata
Project Portfolio - main worksheet, one row per job
Portfolio Summary by Status - auto roll-up by status
Dashboard - portfolio KPIs, top-5 backlogs, aged projects
CSI Reference - canonical division + state lists (hidden, do not edit)
ContrPro - built for builders. Questions: support@contrpro.com

## Company Info
Company Information
Shared metadata referenced by future ContrPro workbooks (COI, Subcontractor, etc.).
Company Name | EIN | Primary State | Workers' Comp Carrier | Bond Carrier | GL Carrier | Notes
EXAMPLE - Carolina Builders LLC | 00-0000000 | TN | Travelers (WC) | Liberty Mutual Surety | The Hartford (GL) | Example row - replace with your company info.

## Project Portfolio
Project Portfolio (one row per job)
Project Number | Project Name | Client | Project Type | Primary CSI Division | State | City | Start Date | Target Completion | Actual Completion | Status | Contract Amount | Approved CO Net | Adjusted Contract | Cost to Date | Estimated Cost at Completion | Projected Gross Margin | Projected Margin % | % Complete | Earned Value | Backlog | Project Manager | Notes
2026-014 | Riverside Office Bldg | Riverside Holdings LLC | New Construction | 03 | TN | Knoxville | 2026-03-01 | 2026-11-30 |  | Active | 1850000 | 22725 |  | 540000 | 1720000 |  |  | 30 |  |  | M. Reyes | On schedule; concrete topping out next month.
2026-021 | Maple Plaza TI Buildout | Maple Capital Partners | Tenant Improvement | 09 | TN | Nashville | 2026-04-15 | 2026-09-15 |  | Mobilizing | 425000 | 0 |  | 18000 | 390000 |  |  | 5 |  |  | M. Reyes | Permits in hand; demo starts next week.
2026-009 | Hillcrest Medical Remodel | Hillcrest Health System | Remodel | 23 | GA | Atlanta | 2026-01-10 | 2026-04-30 | 2026-05-08 | Substantial Completion | 1240000 | 41200 |  | 1198000 | 1215000 |  |  | 98 |  |  | S. Patel | Punchlist in progress; final inspection scheduled.
2026-027 | Eastside Warehouse Roof Repair | Eastside Logistics Inc | Repair | 07 | AL | Birmingham | 2026-05-05 | 2026-05-20 |  | Awarded | 87500 | 0 |  | 0 | 76000 |  |  | 0 |  |  | J. Cole | Insurance claim cleared; mob next Monday.
2026-031 | Civic Center Expansion (BID) | City of Greenville | New Construction | 01 | SC | Greenville |  |  |  | Bidding | 0 | 0 |  | 0 | 0 |  |  | 0 |  |  | M. Reyes | Bid due 2026-06-02; preconstruction cost estimate $4.2M.
TOTALS

## Portfolio Summary by Status
Portfolio Summary by Status (auto roll-up)
Reads from Project Portfolio via COUNTIF/SUMIFS - do not edit. One row per status bucket.
Status | Count | Total Contract | Total Earned Value | Total Cost to Date | Total Backlog | Avg Margin %
Bidding
Awarded
Mobilizing
Active
Substantial Completion
Final
Closed
Lost
TOTALS

## Dashboard
Portfolio Dashboard
Auto-calculated from Project Portfolio. Update that tab - this one stays in sync.
Portfolio KPIs
Total Active Backlog
Total Cost to Date (Active)
Weighted Avg Margin % (Active)
Active Project Count
All Statuses - Total Contract
All Statuses - Total Backlog
Top 5 Largest Backlogs
Rank | Project Name | Backlog
1
2
3
4
5
Aged Projects (past Target Completion, not yet Final/Closed)
Count of aged projects
Backlog tied up in aged projects
To see which projects are aged: open Project Portfolio, filter Target Completion < today and Status not Final/Closed/Lost/Bidding.

## CSI Reference (hidden)
CSI MasterFormat + Reference Lists
Pulled from the same canonical lists as ContrPro Job Costing and Change Order Log. Do not edit.
CSI Division | Division Name | State
01 | General Requirements | AL
02 | Existing Conditions | AK
03 | Concrete | AZ
04 | Masonry | AR
05 | Metals | CA
06 | Wood, Plastics, and Composites | CO
07 | Thermal and Moisture Protection | CT
08 | Openings | DE
09 | Finishes | DC
10 | Specialties | FL
11 | Equipment | GA
12 | Furnishings | HI
13 | Special Construction | ID
14 | Conveying Equipment | IL
21 | Fire Suppression | IN
22 | Plumbing | IA
23 | HVAC | KS
25 | Integrated Automation | KY
26 | Electrical | LA
27 | Communications | ME
28 | Electronic Safety and Security | MD
31 | Earthwork | MA
32 | Exterior Improvements | MI
33 | Utilities | MN
34 | Transportation | MS
35 | Waterway and Marine Construction | MO
40 | Process Interconnections | MT
41 | Material Processing and Handling Equipment | NE
42 | Process Heating, Cooling, and Drying Equipment | NV
43 | Process Gas and Liquid Handling, Purification, and Storage Equipment | NH
44 | Pollution and Waste Control Equipment | NJ
45 | Industry-Specific Manufacturing Equipment | NM
46 | Water and Wastewater Equipment | NY
48 | Electrical Power Generation | NC
49 | Reserved | ND
OH
OK
OR
PA
RI
SC
SD
TN
TX
UT
VT
VA
WA
WV
WI
WY