## Instructions
ContrPro - Accounts Receivable (AR) Tracker
CSI MasterFormat-coded invoice tracker - who owes you what, how old it is, and when to start pulling on the line.
What this workbook is
Five visible tabs plus a hidden CSI Reference. Project Info pins the contract, Invoice Log is the main worksheet, Aging Summary buckets every dollar by how late it is, and Dashboard shows the headline numbers (Total Outstanding, DSO, retainage held).
Every invoice you cut goes in the Invoice Log. The aging math is automatic - you fill in dates and amounts, the workbook tells you who is current, who is 30 days late, and who is past 90 and burning.
Aging buckets - the cadence
Current - not yet past due. Healthy. Do nothing.
1-30 - 1 to 30 days past due. Standard reminder call/email. Most owners pay in this window.
31-60 - 31 to 60 days past due. Escalate to the PM and copy the owner's accountant.
61-90 - 61 to 90 days past due. CFO-level conversation. Stop further work if contract allows.
91-120 - 91 to 120 days past due. Formal demand letter. Pre-lien notices in many states.
120+ - over 120 days. Mechanic's lien window or attorney referral. Statute clock is ticking.
Retainage vs base receivable - keep them separate
Base Amount is the dollar value of work performed this pay period. That is the number the owner owes you against this invoice on the due date.
Retainage Withheld is the percentage (usually 5-10%) the owner holds back per the contract. It is NOT past due until substantial completion - tracked separately so it does not pollute your aging.
Total Invoice = Base Amount. Retainage is logged for visibility only; it gets released at the end of the job via a separate retainage invoice.
Lien waiver workflow
Conditional lien waiver - issue WITH the invoice. Says 'I waive my lien rights conditional on receipt of payment.' This is what owners require to release the check.
Unconditional lien waiver - issue ONLY after the check has cleared. Says 'paid in full, lien rights waived.' Never issue unconditional before the funds settle - this is how contractors lose lien rights.
Lien Waiver Received? column tracks what waivers YOUR subs have given YOU. Yes = unconditional in hand. Conditional = conditional on file. No = open exposure. N/A = self-performed.
When to escalate
60+ days past due: stop and call. PM-to-PM conversation. Document the call in Notes with date and who you talked to. If the answer is 'next week,' put a follow-up on your calendar.
90+ days past due: written demand letter. Reference the contract pay terms, the invoice number, and the amount. Copy the owner principal, not just the PM.
120+ days past due: pre-lien notice if your state requires one (most do; window is typically 60-120 days from last work). Then mechanic's lien before the statute window closes (commonly 90 days from last work, but varies by state). This is attorney territory - do not freelance it.
Days Sales Outstanding (DSO)
DSO is the average number of days it takes you to collect after issuing an invoice. The Dashboard computes it as a dollar-weighted average across all outstanding invoices.
Construction industry benchmark: 60-75 days is normal for commercial GCs, 30-45 days is normal for residential. DSO above 90 means you're financing the project for the owner - margin killer.
Bring DSO down by: invoicing on day-1 of each cycle, issuing conditional waivers at submission, and calling on the 1st late day rather than the 30th.
Tab-by-tab quick start
1. Project Info - fill in Project Name, Number, Client, Contract Amount, PM, and notes on row 4.
2. Invoice Log - one row per invoice. Fill in Invoice Number, dates, customer, CSI Division (dropdown), CSI Code, description, Base Amount, Retainage Withheld, Date Due, Date Paid, Amount Paid. Outstanding, Days Outstanding, and Aging Bucket calculate automatically.
3. Aging Summary - DO NOT edit. Rolls up Invoice Log by bucket.
4. Dashboard - DO NOT edit. Read-only headline numbers and aging panel.
CSI coding rules (must follow)
CSI Division: 2-digit text (01-49). Pick from the dropdown - leading zeros preserved.
CSI Code: 6-digit space-separated, e.g. 23 30 00 for HVAC Air Distribution. Level 3 OK (23 31 13).
Division Name auto-fills from a VLOOKUP against CSI Reference. If it shows blank/error, your CSI Division value does not match the reference list - re-pick from the dropdown.
Color coding cheat sheet
Aging Bucket: green = Current/Paid, yellow = 1-30/31-60, orange = 61-90, red = 91-120 and 120+.
Outstanding: red fill when amount > 0 AND aging is past 60 days - your collection priority queue.
Status: green = Paid, yellow = Sent/Partially Paid, red = Disputed/Written Off.
Weekly cadence
Monday morning: open Dashboard, sort Invoice Log by Days Outstanding desc, call/email anything 14+ days late.
Friday afternoon: log every invoice issued this week and every payment received. Reconcile against the bank.
End of month: tie the Total Outstanding figure to your accounting system AR aging report. They must match.
Tabs in this workbook
Instructions - this tab
Project Info - contract anchor
Invoice Log - CSI-coded invoice line items, the main worksheet
Aging Summary - SUMIFS roll-up by aging bucket
Dashboard - headline AR numbers, DSO, retainage, status counts
CSI Reference - canonical division list (hidden - do not edit)
ContrPro - built for builders. Questions: support@contrpro.com

## Project Info
Project Information
Project Name | Project Number | Client | Contract Amount | Project Manager | Notes
EXAMPLE - Riverside Office Bldg | 2026-014 | Riverside Holdings LLC | 1850000 | Sample PM | Example row - replace with your project.

## Invoice Log
Invoice Log (CSI MasterFormat)
Invoice Number | Date Issued | Customer / Job | CSI Division | CSI Code | Division Name | Description | Base Amount | Retainage Withheld | Total Invoice | Date Due | Date Paid | Amount Paid | Outstanding | Aging Bucket | Days Outstanding | Lien Waiver Received? | Status | Notes
INV-1001 | 2026-03-20 | Riverside Holdings LLC | 03 | 03 30 00 |  | Pay App #2 - Cast-in-place concrete, footings & SOG. | 48500 | 2425 |  | 2026-04-19 | 2026-04-17 | 48500 |  |  |  | Yes | Paid | Paid in full. Unconditional lien waiver on file.
INV-1002 | 2026-04-25 | Riverside Holdings LLC | 05 | 05 12 00 |  | Pay App #3 - Structural steel erection, Level 1-2. | 62300 | 3115 |  | 2026-05-25 |  | 0 |  |  |  | Conditional | Sent | Pay app submitted. Conditional waiver issued; final on receipt.
INV-1003 | 2026-03-06 | Pinnacle Dev Corp | 23 | 23 30 00 |  | Pay App #1 - HVAC rough-in, Level 2 air distribution. | 28750 | 1437.5 |  | 2026-04-05 |  | 0 |  |  |  | No | Partially Paid | Owner remitted $15k against this invoice; $13,750 outstanding. Follow-up email sent 2026-04-22.
INV-1004 | 2026-01-30 | Heartland Builders | 26 | 26 50 00 |  | Pay App #4 - Lighting fixtures & emergency egress install. | 19400 | 970 |  | 2026-03-01 |  | 0 |  |  |  | No | Disputed | Owner disputes 6 fixture count. Demand letter draft prepared; escalate to attorney week of 5/19.
INV-1005 | 2025-12-11 | Apex Industrial | 07 | 07 50 00 |  | Pay App #2 - Membrane roofing, 32 sq install. | 14200 | 0 |  | 2026-01-10 |  | 0 |  |  |  | No | Disputed | 120+ days. Notice of intent to lien filed 2026-04-15. Lien deadline tracking - confirm state statute window.
TOTALS
Formulas:
Aging Bucket = IF(AND([Date Paid]<>"",IFERROR([Amount Paid],0)>=IFERROR([Total Invoice],0),IFERROR([Total Invoice],0)>0),"Paid",IF([Date Due]="","",IF(TODAY()-[Date Due]<=0,"Current",IF(TODAY()-[Date Due]<=30,"1-30",IF(TODAY()-[Date Due]<=60,"31-60",IF(TODAY()-[Date Due]<=90,"61-90",IF(TODAY()-[Date Due]<=120,"91-120","120+")))))))
Days Outstanding = IF(OR([Date Due]="",IFERROR([Outstanding],0)<=0),"",MAX(0,TODAY()-[Date Due]))

## Aging Summary
AR Aging Summary (auto roll-up)
Reads from Invoice Log via COUNTIF / SUMIFS - do not edit this tab directly. One row per aging bucket.
Aging Bucket | Count | Total Outstanding | % of Total
Current
1-30
31-60
61-90
91-120
120+
TOTAL OUTSTANDING

## Dashboard
Accounts Receivable Dashboard
Auto-calculated from Project Info and Invoice Log. Update those tabs - this one stays in sync.
AR Headline
Total Invoiced
Total Paid
Total Outstanding
Total Retainage Held
Days Sales Outstanding (DSO)
Aging Breakdown
Aging Bucket | Count | Outstanding
Current
1-30
31-60
61-90
91-120
120+
TOTAL OUTSTANDING
Count by Status
Status | Count | Amount Outstanding
Sent
Partially Paid
Paid
Disputed
Written Off
ALL INVOICES (any status)

## CSI Reference (hidden)
CSI MasterFormat Division Reference
Pulled from the same canonical list as ContrPro Job Costing. Do not edit.
CSI Division | Division Name
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities
34 | Transportation
35 | Waterway and Marine Construction
40 | Process Interconnections
41 | Material Processing and Handling Equipment
42 | Process Heating, Cooling, and Drying Equipment
43 | Process Gas and Liquid Handling, Purification, and Storage Equipment
44 | Pollution and Waste Control Equipment
45 | Industry-Specific Manufacturing Equipment
46 | Water and Wastewater Equipment
48 | Electrical Power Generation
49 | Reserved