## Instructions
ContrPro - Job Costing Spreadsheet
CSI MasterFormat-coded job cost tracker for general contractors and trade subs.
How to use this workbook
This workbook tracks budget vs. actual cost on a single construction job, organized by CSI MasterFormat division and section. Five tabs work together: Job Info captures the contract, Cost Tracking is where line-item costs go, Division Summary rolls them up, and Dashboard shows the bottom line.
Open the tabs at the bottom of the window in this order: Job Info first, then Cost Tracking, then check Division Summary and Dashboard.
1. Job Info
Fill in Job Name, Job Number, Client, Contract Amount, Start Date, Target Completion, Project Manager, and Estimator on row 4 (the first blank row).
Status is a dropdown: Not Started, In Progress, Substantial Completion, Final, On Hold.
Contract Amount on the FIRST job row (row 4) is the value the Dashboard reads for profit projections. If you track multiple jobs, build a separate file per job.
2. Cost Tracking
Each row is one scope item, coded by CSI Division (2-digit) and CSI Code (6-digit, e.g. 05 12 00).
Pre-populated rows cover the divisions most jobs touch. Add more at the bottom in the empty rows.
Enter Budget, Committed (PO/subcontract value), Actual to Date, and % Complete. Variance and Earned Value are calculated automatically.
Trade column is a dropdown - use it to filter Subcontractor View (just sort or filter by Trade).
Variance turns GREEN when you're under or on budget and RED when you're over.
3. Division Summary
Auto-rolls Cost Tracking up to the division level using SUMIF. Do not type into this tab - it reads from Cost Tracking.
Weighted % Complete is dollar-weighted by Budget so a 100% complete trim line does not skew a 10% complete steel package.
4. Dashboard
Top panel shows Contract Amount, Total Budget, Committed, Actual, Variance, Weighted % Complete, Projected Profit, and Profit Margin.
Projected Profit assumes cost-to-complete tracks linearly with % complete; refine your Actuals weekly for accuracy.
Below the panel is the per-division breakdown - same numbers as Division Summary, formatted for at-a-glance review.
5. CSI MasterFormat coding rules
CSI Division: 2-digit number, leading zero preserved as text (01, 02 ... 33). Do NOT enter as a number or Excel will drop the leading zero.
CSI Code: 6-digit space-separated format - Level 2 (e.g. 05 12 00 for Structural Steel Framing). You can extend to Level 3 (05 12 23) if you need finer detail.
Division Name should match the standard MasterFormat name so subs and architects recognize it on pay apps and change orders.
6. GC vs Subcontractor view
GC View: leave Cost Tracking unfiltered - all divisions visible, Division Summary shows every trade.
Subcontractor View: use Excel/Numbers/Sheets filter on the Trade column (or CSI Division) to show only your scope. The formulas still work because SUMIF references the full range.
7. Weekly update cadence
Friday afternoon: walk the job, update % Complete and Actual to Date on every active line.
Monday morning: review Dashboard - any RED Variance gets a phone call before the week starts.
End of month: reconcile Committed against signed POs and subcontracts; this is your CFO-grade snapshot.
Tabs in this workbook
Instructions - this tab
Job Info - contract and project info (Dashboard reads Contract Amount from here)
Cost Tracking - CSI-coded line items, the main worksheet
Division Summary - SUMIF roll-up by division
Dashboard - totals, projected profit, % complete by division
ContrPro - built for builders. Questions: support@contrpro.com

## Job Info
Job Information
Job Name | Job Number | Client Name | Contract Amount | Start Date | Target Completion | Actual Completion | Status | Project Manager | Estimator | Notes
EXAMPLE - Riverside Office Bldg | 2026-014 | Riverside Holdings LLC | 1850000 | 2026-03-01 | 2026-11-30 |  | In Progress | Sample PM | Sample Estimator | Example row - replace with your job.

## Cost Tracking
Cost Tracking (CSI MasterFormat)
CSI Division | CSI Code | Division Name | Description / Scope Item | Trade | Budget | Committed | Actual to Date | Variance | % Complete | Earned Value | Schedule of Values Item | Notes
01 | 01 10 00 | General Requirements | Summary | General
01 | 01 50 00 | General Requirements | Temporary Facilities and Controls | General
01 | 01 70 00 | General Requirements | Execution and Closeout Requirements | General
02 | 02 30 00 | Existing Conditions | Assessment | General
02 | 02 41 00 | Existing Conditions | Demolition | General
03 | 03 30 00 | Concrete | Cast-in-Place Concrete | Structural Steel
03 | 03 40 00 | Concrete | Precast Concrete | Structural Steel
04 | 04 20 00 | Masonry | Unit Masonry | General
05 | 05 12 00 | Metals | Structural Steel Framing | Structural Steel
05 | 05 31 00 | Metals | Steel Decking | Structural Steel
05 | 05 50 00 | Metals | Metal Fabrications | Structural Steel
06 | 06 10 00 | Wood, Plastics, and Composites | Rough Carpentry | General
06 | 06 20 00 | Wood, Plastics, and Composites | Finish Carpentry | General
07 | 07 20 00 | Thermal and Moisture Protection | Insulation | General
07 | 07 50 00 | Thermal and Moisture Protection | Membrane Roofing | General
07 | 07 90 00 | Thermal and Moisture Protection | Joint Protection | General
08 | 08 10 00 | Openings | Doors and Frames | General
08 | 08 50 00 | Openings | Windows | General
09 | 09 20 00 | Finishes | Plaster and Gypsum Board | General
09 | 09 60 00 | Finishes | Flooring | General
09 | 09 90 00 | Finishes | Painting and Coating | General
10 | 10 50 00 | Specialties | Storage Specialties | General
21 | 21 10 00 | Fire Suppression | Water-Based Fire-Suppression Systems | Mechanical
22 | 22 10 00 | Plumbing | Plumbing Piping | Plumbing
22 | 22 30 00 | Plumbing | Plumbing Equipment | Plumbing
22 | 22 40 00 | Plumbing | Plumbing Fixtures | Plumbing
23 | 23 20 00 | HVAC | HVAC Piping and Pumps | Mechanical
23 | 23 30 00 | HVAC | HVAC Air Distribution | Mechanical
23 | 23 70 00 | HVAC | Central HVAC Equipment | Mechanical
23 | 23 80 00 | HVAC | Decentralized HVAC Equipment | Mechanical
26 | 26 20 00 | Electrical | Low-Voltage Electrical Distribution | Electrical
26 | 26 50 00 | Electrical | Lighting | Electrical
31 | 31 20 00 | Earthwork | Earth Moving | General
31 | 31 60 00 | Earthwork | Special Foundations | General
32 | 32 12 00 | Exterior Improvements | Flexible Paving | General
32 | 32 31 00 | Exterior Improvements | Fences and Gates | General
33 | 33 10 00 | Utilities | Water Utilities | General
TOTALS

## Division Summary
Division Summary (auto roll-up)
Reads from Cost Tracking via SUMIF - do not edit this tab directly.
CSI Division | Division Name | Total Budget | Total Committed | Total Actual | Total Variance | Weighted % Complete | Total Earned Value
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
21 | Fire Suppression
22 | Plumbing
23 | HVAC
26 | Electrical
31 | Earthwork
32 | Exterior Improvements
33 | Utilities
TOTALS

## Dashboard
Job Dashboard
Auto-calculated from Job Info and Cost Tracking. Update those tabs - this one stays in sync.
Job Summary
Contract Amount
Total Budget
Total Committed
Total Actual to Date
Total Variance (Budget - Actual)
Weighted % Complete
Projected Cost at Completion
Projected Profit
Profit Margin %
Per-Division Breakdown
Div | Division Name | Budget | Actual | Variance | % Complete
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
21 | Fire Suppression
22 | Plumbing
23 | HVAC
26 | Electrical
31 | Earthwork
32 | Exterior Improvements
33 | Utilities