## Instructions
ContrPro - Subcontractor Tracker PRO
Prequalification + performance + work history + bonding. The master vendor database. Business / Complete tier.
What this workbook is
Seven visible tabs plus one hidden lookup. Sub Master Record is the deep database - prequal status, license, COI, W9, bonding, EMR, OSHA history, DBE/MBE/WBE, plus a performance scorecard (Schedule, Quality, Safety, Communication, Financial). Work History is a per-project ledger of how each sub actually performed. The remaining tabs are auto-rolled reports: Performance Leaderboard, Compliance Dashboard, Bonding Capacity Roll-Up, Trade Distribution.
This is the FLAGSHIP sub-tracker. If you are awarding > 25 subs/year, running multiple PMs, or carrying $5M+ in subcontracts at any time, this is the tool. If you just need a clean list of who you work with, use the lean Subcontractor_Tracker.xlsx instead.
Prequalification workflow
Step 1 - Add the sub to Sub Master Record with Prequal Status = Pending. Fill in company data, EIN, license, insurance, bonding capacity, EMR. Set Prequal Date to today.
Step 2 - Send the prequal package (financial statements last 3 years, references, safety program, bonding letter, COI sample, license verification). Confirm receipt.
Step 3 - Verify references and license status independently. Pull EMR letter from their insurer. Confirm OSHA 300A logs.
Step 4 - Decision: Approved (full bid list), Conditionally Approved (specific scopes or $ caps only), or Rejected. Set Prequal Renewal Date = +12 months.
Step 5 - Renewal: every Prequal Renewal Date, re-pull financials, COI, license, EMR. Refresh the row. No re-prequal, no awards.
Performance scoring rubric (1-5 each, scored after every job)
Schedule - 5: every milestone hit or beat. 4: minor slip, recovered. 3: schedule slipped but delivered. 2: significant delay, drove other trades. 1: missed completion / abandoned.
Quality - 5: zero punch reopens, owner-grade workmanship. 4: typical punch, closed clean. 3: punch closed slowly. 2: rework required. 1: failed inspection / unacceptable.
Safety - 5: zero recordables, proactive safety. 4: minor first-aid only. 3: one recordable, corrected. 2: multiple incidents. 1: serious injury / OSHA violation.
Communication - 5: proactive RFIs, fast response, owner-facing pro. 4: responsive, clear. 3: reactive only. 2: chasing them for answers. 1: ghosting.
Financial - 5: pay apps clean, no claims. 4: minor pay app errors. 3: one disputed CO. 2: multiple disputes / late lien releases. 1: filed claim or lien against project.
Overall Score is the average. Performance Rating: 4.5+ = A, 3.5-4.4 = B, 2.5-3.4 = C, below 2.5 = D. C is your re-prequal trigger. D is your retirement trigger.
Bonding capacity (Tab 6)
Single Project Bond Capacity - the biggest single contract the sub's surety will bond.
Aggregate Bond Capacity - the total dollar value of bonded work the surety will let them carry at once. Subs get over-extended when active bonded work approaches aggregate.
Available Capacity (Tab 6) = Aggregate - sum of active bonded contracts. A sub at 90%+ of aggregate is tapped out and should not be awarded more bonded work until backlog clears.
Refresh the surety letter annually with the prequal renewal.
Approval gate (formula in Sub Master Record)
Approved? = Yes only if ALL of: Prequal Status = Approved AND COI = Current AND License = Active AND Overall Score >= 3. Any other state returns No.
This is the auto-gate before any award. Read this column on Sub Master, not your gut.
Retiring underperforming subs
Trigger 1: Performance Rating = D for any single completed project AND prior projects average below C. Move Prequal Status to Inactive.
Trigger 2: EMR > 1.0 trending upward for 2 consecutive years. Inactive until they bring it back under 1.0 with a documented safety plan.
Trigger 3: OSHA Recordable Incidents >= 3 in trailing 3 years. Inactive.
Trigger 4: License lapsed > 60 days with no plan to renew. Inactive.
Inactive does NOT mean delete. Keep the row, keep the Work History. You may rehabilitate the relationship later, and the record is the receipt of why you stopped.
Color coding cheat sheet
Prequal Status: green = Approved, yellow = Conditionally Approved / Pending, red = Rejected / Inactive.
COI: green = Current, yellow = Expiring, red = Expired / None.
License: green = Active, yellow = Pending, red = Expired.
Performance Rating: dark green = A, green = B, yellow = C, red = D.
EMR: green when <= 1.0, red when > 1.0.
Approved?: green Yes, red No. This is your final gate.
Tab-by-tab quick start
1. Sub Master Record - one row per sub. Drop in data, score the performance fields after every job. Overall Score, Performance Rating, and Approved? are formulas - do not type.
2. Work History - one row per sub x project. Sub ID links back to Sub Master.
3. Performance Leaderboard - DO NOT edit. Auto-ranks the top 10 by Overall Score.
4. Compliance Dashboard - DO NOT edit. Snapshot of prequal, COI, EMR, bonding, DBE.
5. Bonding Capacity Roll-Up - tracks who has headroom and who is tapped out.
6. Trade Distribution - count + avg performance per trade. Use this when picking who to bid.
7. CSI Reference - hidden. Unhide only if you need to inspect the canonical list.
Tabs in this workbook
Instructions - this tab
Sub Master Record - the deep database (1 row per sub)
Work History - per-project performance ledger
Performance Leaderboard - auto top 10
Compliance Dashboard - totals and risk flags
Bonding Capacity Roll-Up - available bond headroom
Trade Distribution - per-trade roll-up
CSI Reference - canonical division list (hidden)
ContrPro - built for builders. Questions: support@contrpro.com

## Sub Master Record
Sub Master Record
Sub ID | Company Name | DBA / Trade Name | Primary Contact | Secondary Contact | Phone | Email | Address | EIN | Trade | Specialties | CSI Division | Division Name | Years in Business | Annual Revenue | Employees | Office State | Service Area States | Prequal Status | Prequal Date | Prequal Renewal | License # | License State | License Status | COI on File? | COI Expires | W9 on File? | Bonded? | Bonding Company | Single Project Bond Capacity | Aggregate Bond Capacity | DBE/MBE/WBE | DBE Cert Expires | Safety EMR | OSHA Recordable (3yr) | Last Used Date | Score: Schedule | Score: Quality | Score: Safety | Score: Communication | Score: Financial | Overall Score | Performance Rating | Approved? | Notes
S-001 | EXAMPLE - Pacific Steel Erectors | PSE Steel | Marcus Reyes | Tanya Reyes | (555) 213-8842 | marcus@pacificsteel.example | 1240 Industrial Way, Tacoma WA 98421 | 91-2334887 | Structural Steel | Erection, miscellaneous metals, stair fab | 05 |  | 22 | 14500000 | 78 | WA | WA, OR, ID, MT | Approved | 2026-01-15 | 2027-01-15 | WA-CTR-104882 | WA | Active | Current | 2026-09-30 | Yes | Yes | Travelers Casualty | 5000000 | 15000000 | None |  | 0.78 | 0 | 2026-04-12 | 5 | 5 | 5 | 4 | 5 |  |  |  | A-list steel erector. Used on Riverside Office Bldg + Pinnacle. Bonded thru Travelers. EMR 0.78 is best-in-class.
S-002 | EXAMPLE - Apex Plumbing & Mechanical | Apex P&M | Dana Whitfield | Carlos Mendez | (555) 661-0034 | dana@apexpm.example | 5612 Service Rd, Portland OR 97211 | 93-1118822 | Plumbing | Commercial plumbing rough-in, medical gas, fixtures | 22 |  | 18 | 9200000 | 54 | OR | OR, WA | Approved | 2025-11-08 | 2026-11-08 | OR-PLB-77231 | OR | Active | Current | 2026-12-31 | Yes | Yes | Liberty Mutual | 3000000 | 8000000 | None |  | 0.92 | 1 | 2026-05-02 | 4 | 4 | 4 | 5 | 4 |  |  |  | Reliable plumbing partner. Strong on med gas. EMR fine. Pay app cadence monthly, never a friction.
S-003 | EXAMPLE - Bayside Electric LLC |  | Renee Hu | Jon Park | (555) 408-2917 | renee@baysideelec.example | 888 Harbor Blvd, Oakland CA 94606 | 94-2207715 | Electrical | Service entrance, lighting controls, fire alarm | 26 |  | 9 | 4400000 | 28 | CA | CA, NV | Conditionally Approved | 2026-02-22 | 2026-08-22 | CA-C10-1004821 | CA | Active | Expired | 2026-04-30 | Yes | No |  |  |  | MBE | 2027-03-01 | 1.12 | 2 | 2026-02-12 | 3 | 4 | 2 | 3 | 3 |  |  |  | RISK: COI expired 2026-04-30. EMR 1.12 over target. MBE cert valid. Quality fine, safety + paperwork need work.
S-004 | EXAMPLE - North Cascade HVAC | NC HVAC | Sam Petrov | Anna Petrov | (555) 920-4477 | sam@ncascadehvac.example | 201 Mountain View Dr, Bellingham WA 98225 | 91-3447721 | HVAC | VAV controls, RTU install, commissioning support | 23 |  | 14 | 6800000 | 41 | WA | WA | Approved | 2026-03-01 | 2027-03-01 | WA-MEC-55619 | WA | Active | Current | 2027-01-15 | Yes | Yes | Travelers Casualty | 2500000 | 7000000 | None |  | 0.85 | 0 | 2026-03-22 | 5 | 5 | 5 | 5 | 4 |  |  |  | Top-tier HVAC. Strong VAV controls. Approved on Riverside + Pinnacle. Best performer in the HVAC bench.
S-005 | EXAMPLE - Granite West Concrete | Granite West | Tomas Okafor | Marie Okafor | (555) 717-3360 | tomas@granitewest.example | 3300 Plant Rd, Spokane WA 99202 | 91-4498822 | Concrete | Slab on grade, footings, small structural pours | 03 |  | 26 | 12100000 | 65 | WA | WA, ID, MT | Approved | 2025-09-15 | 2026-09-15 | WA-CON-88914 | WA | Active | Current | 2026-11-30 | Yes | Yes | Zurich North America | 4000000 | 10000000 | None |  | 0.88 | 1 | 2026-01-18 | 3 | 4 | 4 | 3 | 4 |  |  |  | Solid for slabs up to ~10K SF. Bigger pours we route to GraniteCore. Schedule slippage is the recurring friction.
S-006 | EXAMPLE - Cornerstone Masonry | Cornerstone | Lila Bennett |  | (555) 332-5511 | lila@cornermason.example | 44 Brick Yard Ln, Boise ID 83702 | 82-2218833 | Masonry | CMU, brick veneer, stone | 04 |  | 6 | 1900000 | 14 | ID | ID, WA, OR | Pending | 2026-04-30 | 2026-10-30 | ID-MSN-21908 | ID | Pending | None |  | No | No |  |  |  | WBE | 2027-05-15 | 1.05 | 0 | [9 empty] | New relationship. Prequal in progress. License renewal + W9 still pending. Hold all awards until full prequal closes. WBE certified.
S-007 | EXAMPLE - Skyline Roofing Co | Skyline | Jorge Alvarez | Maria Alvarez | (555) 224-6611 | jorge@skylineroof.example | 1101 Industrial Pkwy, Reno NV 89502 | 88-1144229 | Roofing | TPO, modified bit, flashing details | 07 |  | 11 | 5300000 | 32 | NV | NV, CA, UT | Approved | 2026-01-30 | 2027-01-30 | NV-ROOF-44520 | NV | Active | Current | 2026-10-15 | Yes | Yes | Liberty Mutual | 2000000 | 5000000 | DBE | 2026-12-31 | 0.95 | 1 | 2026-04-19 | 4 | 4 | 5 | 4 | 4 |  |  |  | TPO + mod-bit specialist. Strong on emergency repair (Riverside wind event). Premium pricing but they show up. DBE cert valid.
S-008 | EXAMPLE - Allied Drywall & Finishes | Allied DW | Kim Park | Eddie Park | (555) 559-2218 | kim@allieddrywall.example | 78 Trade Center Dr, Seattle WA 98108 | 91-5572281 | Drywall | Metal stud framing, drywall, acoustic ceilings, paint | 09 |  | 8 | 3100000 | 22 | WA | WA | Inactive | 2025-06-01 | 2026-06-01 | WA-CTR-203847 | WA | Expired | None |  | Yes | No |  |  |  | None |  | 1.35 | 4 | 2025-11-04 | 2 | 2 | 1 | 2 | 3 |  |  |  | RETIRED from active bid list. EMR 1.35, 4 OSHA incidents last 3 yrs, license expired, COI lapsed. Do not award. Kept on record for history.

## Work History
Work History (per-sub project ledger)
One row per sub x project. Sub ID must match Sub Master Record. Score after every completed contract.
Sub ID | Project Number | Project Name | Year Completed | Contract Value | On-Time? | On-Budget? | Final Quality Rating | Issues / Notes
S-001 | P-2024-014 | Riverside Office Building | 2024 | 1850000 | Yes | Yes | 5 | Excellent erection schedule. Zero punch issues.
S-001 | P-2025-007 | Pinnacle Tower Phase 1 | 2025 | 2650000 | Yes | Yes | 5 | On schedule throughout. Stair fab quality top-tier.
S-002 | P-2024-018 | Northgate Medical Plaza | 2024 | 920000 | Yes | Partial | 4 | Med gas changes drove $42K cost growth - sub flagged early.
S-002 | P-2025-003 | Bayview Tenant Improvement | 2025 | 310000 | Yes | Yes | 4 | Clean job. Fixture coordination handled well.
S-003 | P-2025-009 | Harbor District Retail | 2025 | 480000 | Partial | No | 3 | Two safety stand-downs. Schedule slipped 14 days. Cost overrun $28K.
S-004 | P-2024-014 | Riverside Office Building | 2024 | 1120000 | Yes | Yes | 5 | VAV controls commissioned 5 days early. Owner thrilled.
S-004 | P-2025-007 | Pinnacle Tower Phase 1 | 2025 | 1580000 | Yes | Yes | 5 | Same crew as Riverside. Same A+ result.
S-005 | P-2024-011 | Eastpoint Distribution Center | 2024 | 1350000 | No | Partial | 4 | Slab pours delayed 11 days due to rebar lead time. Quality fine.
S-007 | P-2024-014 | Riverside Office Building (storm repair) | 2024 | 68000 | Yes | Yes | 5 | Emergency wind-event repair, mobilized in 36 hrs.
S-008 | P-2024-006 | Sunnyside Office Refit | 2024 | 240000 | No | No | 2 | Schedule slip 21 days. Punch list reopened twice. Crew safety issue noted.

## Performance Leaderboard
Performance Leaderboard
Top 10 subs by Overall Score. Auto-ranked from Sub Master Record. Do not edit - update scores on the master tab and this re-sorts.
Rank | Sub ID | Company Name | Trade | Overall Score | Rating | Last Used
1
2
3
4
5
6
7
8
9
10

## Compliance Dashboard
Compliance Dashboard
Auto-rolled from Sub Master Record. Update that tab - this stays in sync.
Roster Snapshot
Total Subs in Database
Total Approved Subs
Total Pending Prequal
Average Performance Score (Approved subs)
Risk Flags
Subs with Expiring COIs (next 30 days)
Subs with Expired COIs
Subs with Expired License
Subs with EMR > 1.0 (safety concern)
Inactive / Rejected Subs
Bonding & Diversity
Bonded Subs (count)
Total Aggregate Bonding Capacity ($)
DBE Certified
MBE Certified
WBE Certified

## Bonding Capacity Roll-Up
Bonding Capacity Roll-Up
Per-sub bonding headroom. Active Project Count + Contract Value $ are summed from Work History (current year only). Available = Aggregate - Active. Subs near 0 are tapped out.
Sub ID | Company Name | Single Project Capacity | Aggregate Capacity | Active Bonded Value (current yr) | Available Capacity

## Trade Distribution
Trade Distribution
Per-trade roll-up: total in database, count approved, and average performance score. Pulls live from Sub Master Record.
Trade | Total Count | Approved Count | Avg Performance Score
General
Mechanical
Electrical
Plumbing
Structural Steel
HVAC
Roofing
Concrete
Masonry
Drywall
Flooring
Painting
Earthwork
Fire Suppression
Other
TOTALS

## CSI Reference (hidden)
CSI MasterFormat Division Reference
Canonical list - do not edit. Feeds the CSI Division dropdown and VLOOKUPs in Sub Master Record.
CSI Division | Division Name
01 | General Requirements
02 | Existing Conditions
03 | Concrete
04 | Masonry
05 | Metals
06 | Wood, Plastics, and Composites
07 | Thermal and Moisture Protection
08 | Openings
09 | Finishes
10 | Specialties
11 | Equipment
12 | Furnishings
13 | Special Construction
14 | Conveying Equipment
21 | Fire Suppression
22 | Plumbing
23 | HVAC
25 | Integrated Automation
26 | Electrical
27 | Communications
28 | Electronic Safety and Security
31 | Earthwork
32 | Exterior Improvements
33 | Utilities
34 | Transportation
35 | Waterway and Marine Construction
40 | Process Interconnections
41 | Material Processing and Handling Equipment
42 | Process Heating, Cooling, and Drying Equipment
43 | Process Gas and Liquid Handling, Purification, and Storage Equipment
44 | Pollution and Waste Control Equipment
45 | Industry-Specific Manufacturing Equipment
46 | Water and Wastewater Equipment
48 | Electrical Power Generation
49 | Reserved