Project ID + Attendance

Contract Documents

Permit + AHJ + Utility

Drawing + Spec Review

Long-Lead Material (Gear, Generator, ATS)

Submittal Schedule

Site Logistics

Multi-Trade Coordination

Inspection Sequence + AHJ Workflow

Safety Program Confirmation

Insurance, Bonds, Licenses

Schedule + Manpower Forecast

Action Items

Signatures

| Project Name + Number | [fill] |
| --- | --- |
| Project Address | [fill] |
| Electrical Contract Value | [$] |
| Notice-to-Proceed | [date] |
| Substantial Completion Target | [date] |
| Service Size | [A / V / Φ] |

| Role | Name | Phone / Email |
| --- | --- | --- |
| GC PM | [fill] |  |
| GC Superintendent | [fill] |  |
| GC Safety Officer | [fill] |  |
| EC Project Mgr | [fill] |  |
| EC Superintendent | [fill] |  |
| EC Foreman | [fill] |  |
| Master Electrician of Record | [fill] |  |
| Electrical Engineer (EOR) | [fill] |  |
| AHJ Electrical Inspector | [often async] |  |
| Utility Coordinator | [fill] |  |
| Switchgear Vendor | [fill] |  |
| Fire Alarm Sub Rep | [fill] |  |
| Low Voltage / IT | [fill] |  |

Signed subcontract on file with all exhibits.

Scope boundaries with adjacent trades documented (FP / Plumb / Mech).

Inclusions / exclusions list signed.

Change-order process documented (authorization + dollar threshold + lead time).

Pay-app schedule + retention % + lien-waiver type.

Liquidated damages + curing process documented.

Warranty period documented.

| Electrical Permit # | [#] |
| --- | --- |
| Adopted NEC Edition | [NEC 2023 + amendments] |
| Inspection Request Method | [Portal + lead time] |
| Re-Inspection Fee | [$] |
| Utility Coordinator | [Power co + acct + contact] |
| Service Meter Set Date Target | [Date] |
| Utility Service-Drop Spec | [Underground / overhead / 4-jaw / 5-jaw / CT] |
| Cross-trade Permits (FP/LV) | [fill] |

Current revision set at GC + EC trailers.

All RFIs dispositioned.

Single-line diagram cross-checked against panel schedules + load summary.

Fault-current calc + breaker AIC ratings verified.

Arc-flash study reviewed (if engineered study provided).

Voltage drop calc verified against branch + feeder lengths.

Conduit + cable schedules cross-checked.

Lighting layout vs. reflected ceiling plan reconciled.

Sleeve + opening schedule reconciled with structural + arch.

Above-ceiling overlay reviewed; clashes flagged.

Below-slab utility overlay reviewed.

Wall + floor penetrations through rated assemblies — UL listings identified.

Trapeze + structural-attachment locations approved by EOR.

Working clearances (NEC 110.26) verified for all gear locations.

| Item | Vendor | PO Date | Lead Time | Needed Date |
| --- | --- | --- | --- | --- |
| Switchboard (service entrance) | [fill] |  |  |  |
| Standby generator (if scope) | [fill] |  |  |  |
| ATS / paralleling switchgear | [fill] |  |  |  |
| Custom panelboards (high amp / MCC) | [fill] |  |  |  |
| Specialty fixtures (architectural / custom) | [fill] |  |  |  |
| Fire alarm panel + devices | [fill] |  |  |  |
| Lighting controls system | [fill] |  |  |  |

| Submittal | Spec Section | Submit By | Approval By |
| --- | --- | --- | --- |
| Wire + cable | 26 05 19 | [fill] |  |
| Raceway | 26 05 33 | [fill] |  |
| Grounding + bonding | 26 05 26 | [fill] |  |
| Service entrance + switchboard | 26 24 13 | [fill] |  |
| Panelboards | 26 24 16 | [fill] |  |
| Disconnects + circuit breakers | 26 28 | [fill] |  |
| VFDs + starters | 26 29 | [fill] |  |
| Generator + ATS | 26 32 / 26 36 | [fill] |  |
| Lighting fixtures + lamps | 26 51 / 26 52 | [fill] |  |
| Lighting controls | 26 09 | [fill] |  |
| Fire alarm system | 28 31 | [fill] |  |
| Acceptance test plan (NETA) | 26 08 | [fill] |  |

Site access + parking + hours.

Lay-down area for raceway + gear.

Temporary power source + amperage available.

Hoisting/crane coordination for gear deliveries.

Lift / scissor lift rental schedule.

Dumpster + recycling for scrap metal.

Security + badge access.

| Coordination Item | Trades | Resolution |
| --- | --- | --- |
| Above-ceiling priority | EC / Mech / Plumb / FP | BIM / coord drawings |
| Slab sleeves + embeds | EC / Concrete | Sleeve schedule 7-10 days pre-pour |
| Wall rough-in for boxes | EC / Framing | Layout markup on framing |
| Underground duct bank | EC / Site / Plumb | Locate ticket + survey |
| Final connection to plumbing/mech equipment | EC / Plumb / Mech | Scope-split confirmation |
| Lighting layout vs. ductwork / sprinkler | EC / Mech / FP | RCP overlay |
| Fire-alarm device locations | EC / FA sub | Coordinated layout |
| Switchgear placement + working clearance | EC / Arch / Owner | NEC 110.26 verified |

| Inspection | Schedule Trigger | Lead Time |
| --- | --- | --- |
| Underground Raceway | Pre-backfill | [hours] |
| Rough-In | Pre-drywall | [hours] |
| Service / Meter | Pre-energize | [hours] |
| Pre-Energization Acceptance Test | Pre-utility tie | [hours] |
| Final Electrical | Pre-TCO | [hours] |

SSEP reviewed + signed.

LOTO program — locks/tags issued, training current.

NFPA 70E training current; EWP forms on site; arc-rated PPE inventoried.

Arc-flash study reviewed; labels ready for installation.

Hot work permit program.

Excavation Competent Person identified.

Lift / scissor-lift training current.

GFCI on every temp-power circuit verified.

Hazcom / SDS for adhesives, sealants, cleaners.

Toolbox-talk schedule; first-aid + AED locations.

| Workers' Comp | [Carrier + limit + expiry] |
| --- | --- |
| General Liability | [Carrier + limit + expiry] |
| Auto Liability | [Limit + expiry] |
| Umbrella / Excess | [Limit + expiry] |
| Performance Bond | [Surety + limit] |
| EC State License | [# + expiry] |
| Master Electrician License | [Name + # + expiry] |
| NICET / Fire Alarm Cert | [# + expiry] |
| NETA Cert (if AET in scope) | [# + expiry] |

| Phase | Weeks | Foremen | Journeymen | Apprentices |
| --- | --- | --- | --- | --- |
| Underground | [fill] |  |  |  |
| Rough-In | [fill] |  |  |  |
| Service + Gear set | [fill] |  |  |  |
| Trim Out | [fill] |  |  |  |
| Acceptance Testing + Commissioning | [fill] |  |  |  |

| # | Action Item | Owner | Due Date | Closed? |
| --- | --- | --- | --- | --- |
| 1 | [fill] |  |  |  |
| 2 | [fill] |  |  |  |
| 3 | [fill] |  |  |  |
| 4 | [fill] |  |  |  |
| 5 | [fill] |  |  |  |
| 6 | [fill] |  |  |  |
| 7 | [fill] |  |  |  |
| 8 | [fill] |  |  |  |
| 9 | [fill] |  |  |  |
| 10 | [fill] |  |  |  |

Distribute: GC trailer, EC field trailer, EC office, owner's rep.