## Instructions
PUNCH LIST + AS-BUILT LOG — INSTRUCTIONS
PURPOSE
Single running log of every closeout item: punch items, as-built deliverables, O&M
manual sections, and final submissions. Tabs are independent — fill what applies.
PUNCH LIST WORKFLOW
1. Self-punch before GC walk. Walk every fixture + system; capture deficiencies.
2. Add each item to the Punch List tab with: location, fixture / system, description,
priority, assigned to, target date, photo reference.
3. As items clear, set Status='Closed' + record closed-date + closed-by.
4. Closed Punch Archive tab pulls a filter-view of closed items for retention payback.
AS-BUILT WORKFLOW
1. During construction, foreman maintains daily redlines on the field set.
2. At closeout, transfer all redlines to a clean as-built set.
3. As-Built Documentation Checklist tracks every drawing sheet + the redline transfer
status. Don't sign off until every sheet is checked.
O&M MANUAL
Use the index tab to confirm every required section is populated before binding.
FINAL SUBMISSIONS
Use the Final Submissions Tracker to confirm every required document went to every
required recipient (Owner / GC / AHJ / Water Purveyor). Cleared retention depends
on this tab.
DOCUMENT VERSION
Punch_List_and_AsBuilt_Log.xlsx v1.0 — 2026-05-19
ContrPro Complete Tier · Plumbing Trade Pack

## Punch List
PUNCH LIST — open + closed running log
# | Location (Bldg/Floor/Room) | System / Fixture | Description | Priority (H/M/L) | Assigned To | Target Date | Status (Open/Closed) | Closed Date | Photo Ref

## Closed Archive
CLOSED PUNCH ARCHIVE (filter view — paste closed rows for retention)
# | Location | System / Fixture | Description | Priority | Closed By | Closed Date | Photo Ref

## As-Built Checklist
AS-BUILT DOCUMENTATION CHECKLIST
Sheet # | Drawing Title | Redlines (description) | Transferred Y/N | Verified By | Date
P-0.0 | Plumbing Cover / Index
P-1.0 | Underground Sanitary Plan
P-1.1 | Underground Storm Plan
P-1.2 | Underground Water + Gas Plan
P-2.0 | First-Floor Plumbing
P-2.1 | Second-Floor Plumbing
P-2.2 | Roof Plumbing Plan
P-3.0 | Sanitary Riser Diagrams
P-3.1 | Water Riser Diagrams
P-3.2 | Gas Riser + Sizing
P-4.0 | Plumbing Details
P-5.0 | Plumbing Schedules + Fixture Cuts
P-6.0 | Specifications Volume

## O&M Index
O&M MANUAL — REQUIRED SECTION INDEX
Tab | Section | Contents | Populated Y/N | Verified By
1 | Cover Sheet | Project name / address / contractor / version
2 | Table of Contents | Sectional TOC + page numbers
3 | System Overview | Schematic + narrative description
4 | Equipment Data | Cut sheets — water heaters / boosters / pumps / interceptors / BFPs
5 | Approved Submittals | Every approved submittal in CSI order
6 | Mfr O&M Booklets | Original manufacturer booklets
7 | Test Reports | Pressure / DWV / gas test logs + disinfection cert + BFP initial tests
8 | As-Builts | Reduced + full-size in rear pocket
9 | Warranties | Contractor warranty letter + mfr warranty cards
10 | Maintenance Schedule | Recommended PM intervals + tasks
11 | Vendor Contacts | Service techs / suppliers / water purveyor
12 | Emergency Procedures | Shutoffs / contacts / backup vendor

## Final Submissions
FINAL SUBMISSIONS TRACKER
Document | Recipient | Sent Date | Confirmed | Notes
Pressure test log
DWV / stack test results
Gas pressure test report
Backflow initial test reports
Disinfection certificate
Final as-built drawings (paper)
Final as-built drawings (PDF)
Final as-built drawings (CAD)
O&M Manual (binder)
O&M Manual (PDF/USB)
Warranty letter
Equipment registrations
Conditional final lien waiver
Unconditional final lien waiver
Punch list closeout sign-off